## Record of Changes
Date | Person/Company | Changes Made
2025-06-12 | Chris Webb/Worley | Rev 1 Finalised for sites: Quinns Beach, Grannies Beach, Grace Darling (Lancelin), Seabird, C.Y. Oconnor, Kwinana Industrial, Kwinana Town Beach, Rockingham Townsite, North Point Peron, Mandurah Northern Beaches, Wonnerup, Emu Pt
2025-11-21 | Izzy Utley/DTMI | Updated: Added 2024 works at Quinns Beach , 2025 works at Grannies, 2024 works Grace Darling, Dec 2024 works CY Oconnor, Update to Kwinana Town Beach nourishment volumes.
2026-06-15 | Lucya Roncevich/DTMI | Checking/updating of Point Peron volumes and checking of minor inconsistencies for some sites.

## Quinns Beach
|  | Department of Transport Quinns Beach Database of Coastal Management History Date Populated: 15/01/2024 Last Updated: 21/11/2025 | [5 empty] | 5 = Good condition, fully functional 3 = Moderate condition, still functional 1 = Poor condition, not functional |  |  | Offshore breakwater: Length, material (rock/GSC), distance to shore, spacing/interval; crest level (rock/GSC), distance to shore, spacing/interval; crest level Groyne: Length, material (rock/GSC/timber), spacing/interval; crest level Seawall or revetment: Length, material (rock/GSC); crest level
Site | Name | Ownership | Mgmt Hierarchy | Description | Lat | Lon | Year of Construction (completion) | Current Condition | Condition Comments | Past damage/repairs/improvements; | Structure Information (see above) | Remaining design life (while performing intended function); | Record added by
Quinns Beach | Sand nourishment |  | Protect | 1264m3 of sand placed at Queenscliff Park Carpark |  |  | 2024-05-03 | [5 empty] | IU/LR
Quinns Beach | Sand nourishment |  | Protect | 1358m3 at Quinns Dog Beach, north of Groyne 3 |  |  | 2024-05-03 | [5 empty] | IU/LR
Quinns Beach | Sand nourishment |  | Protect | 1837m3t of sand placed at Quinns Beach (adj. to FS Carpark) |  |  | 2024-05-03 | [5 empty] | IU/LR
Quinns Beach | Sand nourishment |  | Protect | 2580m3 of sand placed at QB13 (north side of Groyne 3) |  |  | 2023-05-01 | [5 empty] | CW
Quinns Beach | Sand nourishment |  | Protect | 3225m3 of sand placed at FS Carpark |  |  | 2023-05-01 | [5 empty] | CW
Quinns Beach | Dune fencing repairs and sand redistribution |  | Protect | Dune and windbreak fencing repairs and sand redistribution |  |  | 2023-02-01 | [5 empty] | CW
Quinns Beach | GSC Repairs |  | Protect | Recovered buried and dislodged GSC from beach |  |  | 2022-08-01 | [5 empty] | CW
Quinns Beach | Staircase repairs |  | Protect | Stair repairs - minor |  |  | 2022-08-01 | [5 empty] | CW
Quinns Beach | Sand nourishment |  | Protect | 2580m3 of sand placed at QB13 (north side of Groyne 3) |  |  | 2022-04-01 | [5 empty] | CW
Quinns Beach | Sand nourishment |  | Protect | 2580m3 of sand placed at FS Carpark (north side of Groyne 1) |  |  | 2022-04-01 | [5 empty] | CW
Quinns Beach | Sand nourishment |  | Protect | 1935m3 of sand placed at FS Carpark (north side of Groyne 1) |  |  | 2021-11-01 | [5 empty] | CW
Quinns Beach | Refurbishment of groyne 1 |  | Protect | Maintenance and upgrade | -31.67196° | 115.690347° | 2021-04-01 | 5 |  |  |  | 48 | CW
Quinns Beach | Sand nourishment |  | Protect |  |  |  | 2021-04-01 | [5 empty] | CW
Quinns Beach | Sand nourishment |  | Protect | 1290m3 of sand placed north of groyne 3 |  |  | 2021-04-01 | [5 empty] | CW
Quinns Beach | Sand nourishment |  | Protect | 1290m3 of sand placed north of groyne 4 |  |  | 2021-04-01 | [5 empty] | CW
Quinns Beach | Sand nourishment |  | Protect | 4970m3 of sand placed at FS carpark |  |  | 2020-06-01 | [5 empty] | CW
Quinns Beach | Sand nourishment |  | Protect | 2130m3 of sand placed at Groyne 3 |  |  | 2020-06-01 | [5 empty] | CW
Quinns Beach | Sand nourishment |  | Protect | 1935m3 of sand placed at Groyne 4 |  |  | 2020-06-01 | [5 empty] | CW
Quinns Beach | Extension of existing groyne 3 |  | Protect | Extended by 15m | -31.663794° | 115.688793° | 2019-12-01 | 5 |  |  | 75m long, limestone, crest = 4.5-6.0m, max armour 6.6T | 46 | CW
Quinns Beach | Sand nourishment |  | Protect | 1935m3 of sand placed at Groyne 4 |  |  | 2019-06-01 | [5 empty] | CW
Quinns Beach | Sand nourishment |  | Protect | 12260m3 of nourishment associated with groyne 2 upgrades |  |  | 2019-02-02 | [5 empty] | CW
Quinns Beach | Extension of existing groyne 2 | CoW | Protect | Extended by 45m | -31.667773° | 115.689575° | 2019-02-01 | 5 |  |  | 85m long, limestone, crest = 4.5-6.0m, max armour 6.6T | 46 | CW
Quinns Beach | Sand nourishment |  | Protect | 7097m3 of sand placed (assumed apart of Groyne 4) |  |  | 2018-06-02 | [5 empty] | CW
Quinns Beach | Groyne 4 construction |  | Protect | 60m long northern groyne | -31.658903° | 115.687278° | 2018-06-01 | 5 |  |  | 60m long, limestone, crest = 4.5-6.0m, max armour 6.6T | 45 | CW
Quinns Beach | Access ramp construction |  | Protect | Associated with groyne 4 construction |  |  | 2018-06-01 | [5 empty] | CW
Quinns Beach | Sand nourishment |  | Protect | 8065m3 of sand placed at FS Carpark |  |  | 2018-02-01 | [5 empty] | CW
Quinns Beach | Sand nourishment |  | Protect | 6450m3 placed at FS Carpark |  |  | 2017-03-01 | [5 empty] | CW
Quinns Beach | Sand nourishment |  | Protect | 6450m3 placed at Groyne 3 |  |  | 2017-03-01 | [5 empty] | CW
Quinns Beach | Sand nourishment |  | Protect | 5806m3 placed at groyne 3 |  |  | 2016-05-01 | [5 empty] | CW
Quinns Beach | Sand nourishment |  | Protect | 1290m3 placed at Carpark |  |  | 2016-05-01 | [5 empty] | CW
Quinns Beach | Sand nourishment |  | Protect | 3870m3 of sand placed at FS Carpark |  |  | 2015-05-01 | [5 empty] | CW
Quinns Beach | GSC Seawall Construction |  | Protect | 280m of GSC along FS Park & dune rehabilitation | -31.673266° | 115.691010° | 2014-01-01 | 5 |  |  |  |  | CW
Quinns Beach | Sand nourishment |  | Protect | 16780m3 at FS carpark |  |  | 2014-01-01 | [5 empty] | CW
Quinns Beach | Seawall repairs |  | Protect | Adhoc repair of limestone seawall | -31.670633° | 115.690714° | 2012-11-01 | 2 |  |  |  |  | CW
Quinns Beach | Groyne Maintenance (1-3) & Seawall repairs |  | Protect | Required to improve the condition of the three groyne structures and repair the seawall |  |  | 2008-01-01 | [5 empty] | CW
Quinns Beach | Sand nourishment |  | Protect | 19355m3 nourishment |  |  | 2006-10-01 | [5 empty] | CW
Quinns Beach | Sand nourishment |  | Protect | 32258m3 nourishment |  |  | 2004-11-01 | [5 empty] | CW
Quinns Beach | Sand nourishment |  | Protect | 67097m3 nourished to support new groyne |  |  | 2004-02-01 | [5 empty] | CW
Quinns Beach | Groyne 3 construction |  | Protect |  | -31.663794° | 115.688793° | 2004-02-01 | 5 |  |  |  |  | CW
Quinns Beach | Sand nourishment |  | Protect | 60645m3 nourished to support new groyne |  |  | 2003-03-01 | [5 empty] | CW
Quinns Beach | Groyne 1 construction |  | Protect |  | -31.67196° | 115.690347° | 2003-03-01 | 5 |  |  |  |  | CW
Quinns Beach | Groyne 2 construction |  | Protect |  | -31.667773° | 115.689575° | 2003-03-01 | 5 |  |  |  |  | CW
Quinns Beach | Seawall Construction |  | Protect | Emergency coastal protection works; limestone boulder seawall placed in front of car park |  |  | 2002-01-01 | 2 |  |  |  |  | CW
Quinns Beach | Artificial Headland Construction |  | Protect | Construction of artificial headlandat cusp where Quinns beach naturally deviates northwards | -31.675838° | 115.691028° | 1977-01-01 | 1
Note on E5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Used a density conversion of 1.55T/m3 of trucked sand (tonnes) placed in situ (m3).

## Grannies Beach
|  | Department of Transport Grannies Beach Database of Coastal Management History | Department of Transport Grannies Beach Database of Coastal Management History Date Populated: 01/05/2024 Last Updated: 21/11/2025 |  |  | 5 = Good condition, fully functional 3 = Moderate condition, still functional 1 = Poor condition, not functional |  |  | Offshore breakwater: Length, material (rock/GSC), distance to shore, spacing/interval; crest level (rock/GSC), distance to shore, spacing/interval; crest level Groyne: Length, material (rock/GSC/timber), spacing/interval; crest level Seawall or revetment: Length, material (rock/GSC); crest level
Site | Name | Ownership | Mgmt Hierarchy | Description | Year of Construction (completion) | Current Condition | Condition Comments | Past damage/repairs/improvements; | Structure Information | Remaining design life (while performing intended function); | Record added by
Grannies/Surf Beach | Grannies retaining wall emergency repairs |  | Protect | Remedial works for overturning failure of retaining wall at Grannies Beach | 2025-10-01 | [5 empty] | IU
Grannies/Surf beach | Sand/stabilisation - Stage 3 revegetation |  | Protect | Surf beach nature-based stablisation | 2024-04-01 | [5 empty] | CW
Grannies/Surf beach | Sand/stabilisation - Stage 3 Concrete |  | Protect | 80m Surf beach stablisation works, insitu sand/concrete mixture | 2023-11-01 | N/A |  |  |  |  | CW
Grannies/Surf beach | Sand/stabilisation - Stage 2 Concrete + revegetation |  | Protect | 150m Surf beach stablisation works, insitu sand/concrete mixture. Includes removal of excess rock from seawall. | 2021-02-01 | N/A |  |  |  |  | CW
Grannies/Surf beach | Grannies retaining wall emergency repairs |  | Protect | Concrete poured to provide support to cracking retaining wall | 2021-02-01 | 3 | Cracks present, poured concrete repairs scoured |  |  |  | CW
Grannies/Surf beach | Sand/stabilisation - Stage 1 Concrete + revegetation |  | Protect | 50m Surf beach stablisation works, insitu sand/concrete mixture | 2020-01-01 | [5 empty] | CW
Grannies/Surf beach | Seawall stage 3 |  | Protect | 30m extension north of phase 2 | 2014-01-01 | 5 |  |  | Seawall or revetment: Length = 30m, Rock (basalt); crest level = 4.6-5.5m, Armour = 0.8 - 3T |  | CW
Grannies/Surf beach | Sand nourishment |  | Protect | 1,000m3 placed at Grannies Beach (sourced from Dune Sand) | 2011-12-01 | [5 empty] | CW
Grannies/Surf beach | Sand nourishment |  | Protect | 1,800m3 placed at Grannies Beach (sourced from Dune Sand) | 2011-07-01 | [5 empty] | CW
Grannies/Surf beach | Sand nourishment |  | Protect | 2,500m3 of sand placed at Grannies and surf beach | 2011-01-01 | [5 empty] | CW
Grannies/Surf beach | Sand nourishment |  | Protect | 500m3 placed at Surf Beach (sourced from Dune Sand) | 2011-01-01 | [5 empty] | CW
Grannies/Surf beach | Seawall stage 2 |  | Protect | Grannies seawall - 170m northwards of phase 1 | 2011-01-01 | 5 |  |  | Seawall or revetment: Length = 170m, Rock (basalt); crest level = 4.6-5.5m, Armour = 0.8 - 3T |  | CW
Grannies/Surf beach | Seawall stage 1 |  | Protect | Grannies seawall - 30m at southern end of caravan park | 2010-06-01 | 5 |  |  | Seawall or revetment: Length = 30m, Rock (basalt); crest level = 4.6-5.5m, Armour = 0.8 - 3T |  | CW
Grannies/Surf beach | Coastal Protection Works |  | Protect | Coastal Protection Works - Grannies Beach | 2010-01-01 | [5 empty] | CW
Grannies/Surf beach | Emergency protection works |  | Protect | Emergency protection works - Grannies beach | 2010-01-01 | [5 empty] | CW
Grannies/Surf beach | Sand nourishment |  | Protect | 13,500m3 placed at Grannies and Surf Beach (sourced from coarse sand/shells from south of Port Denison) | 2010-01-01 | [5 empty] | CW
Grannies/Surf beach | GSC protextion |  | Protect | GSCs placed at toe of limestone retaining wall at Grannies Beach, repairs also made to retaining wall. | 2009-01-01 | [5 empty] | CW
Grannies/Surf beach | Sand nourishment |  | Protect | 20,000m3 placed in front of Caravan Park (sourced from Dune Sand at Airstrip) | 1999-01-01 | [5 empty] | CW
Grannies/Surf beach | Port Denison Breakwater Construction |  |  | Marina opened | 1979-01-01 | [5 empty] | CW
Note on E3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Is this the limestone retaining wall or surf beach stabilisation works?

## Grace Darling (Lancelin)
|  | Department of Transport Grace Darling Park Database of Coastal Management History Date Populated: 01/08/2024 Last Updated: 21/11/2025 |  |  |  | 5 = Good condition, fully functional 3 = Moderate condition, still functional 1 = Poor condition, not functional |  |  | Offshore breakwater: Length, material (rock/GSC), distance to shore, spacing/interval; crest level (rock/GSC), distance to shore, spacing/interval; crest level Groyne: Length, material (rock/GSC/timber), spacing/interval; crest level Seawall or revetment: Length, material (rock/GSC); crest level
Site | Name | Ownership | Mgmt Hierarchy | Description | Year of Construction (completion) | Current Condition | Condition Comments | Past damage/repairs/improvements; | Structure Information (see above) | Remaining design life (while performing intended function); | Record added by
Lancelin | Sand nourishment |  | Protect | 2,500m3 used to nourish Grace Darling beaches | 2024-11-29 | [5 empty] | IU
Lancelin | Sand nourishment |  | Protect | 2654m3 used to nourish Grace Darling beaches, sourced from local sand pits | 2023-12-01 | [5 empty] | CW
Lancelin | Sand nourishment |  | Protect | 4460m3 used to nourish Grace Darling beaches | 2022-12-01 | [5 empty] | CW
Lancelin | Sand nourishment |  | Protect | 2194m3 used to nourish Grace Darling beaches | 2021-12-01 | [5 empty] | CW
Lancelin | Sand nourishment (dredge disposal) |  | Protect | 8000m3 of dredge disposal used to nourish Grace Darling beaches, DoT dredging campaign brought forward due to erosion at GD | 2020-05-01 | [5 empty] | CW
Lancelin | Sand nourishment |  | Protect | 1613m3 used to nourish Grace Darling beaches | 2019-12-01 | [5 empty] | CW
Lancelin | Sand nourishment |  | Protect | 429m3 used to nourish Grace Darling beaches | 2019-06-01 | [5 empty] | CW
Lancelin | Sand nourishment |  | Protect | 382m3 used to nourish Grace Darling beaches | 2018-12-01 | [5 empty] | CW
Lancelin | Sand nourishment (dredge disposal) |  | Protect | 4500m3 of dredge disposal used to nourish Grace Darling beaches | 2017-05-01 | [5 empty] | CW
Lancelin | Sand nourishment |  | Protect | 1185m3 used to nourish Grace Darling beaches | 2016-12-01 | [5 empty] | CW
Lancelin | Sand nourishment |  | Protect | 1613m3 used to nourish Grace Darling beaches | 2016-04-01 | [5 empty] | CW
Lancelin | Sand nourishment |  | Protect | 3500m3 used to nourish Grace Darling beaches | 2015-05-01 | [5 empty] | CW
Lancelin | Sand nourishment |  | Protect | 1200m3 used to nourish Grace Darling beaches | 2014-11-01 | [5 empty] | CW
Lancelin | Sand nourishment |  | Protect | 4500m3 used to nourish Grace Darling beaches | 2013-12-01 | [5 empty] | CW
Lancelin | Sand nourishment |  | Protect | 1000m3 used to nourish Grace Darling beaches | 2012-12-01 | [5 empty] | CW
Lancelin |  |  |  | Initial construction of Grace Darling Park facilities | 1994-01-01 | [5 empty] | CW
Note on C1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Add in date updated

## Seabird
|  | Department of Transport Seabird Database of Coastal Management History Date populated: 01/01/2025 Last Updated: 01/01/2025 |  |  |  | 5 = Good condition, fully functional 3 = Moderate condition, still functional 1 = Poor condition, not functional |  |  | Offshore breakwater: Length, material (rock/GSC), distance to shore, spacing/interval; crest level (rock/GSC), distance to shore, spacing/interval; crest level Groyne: Length, material (rock/GSC/timber), spacing/interval; crest level Seawall or revetment: Length, material (rock/GSC); crest level
Site | Name | Ownership | Mgmt Hierarchy | Description | Year of Construction (completion) | Current Condition | Condition Comments | Past damage/repairs/improvements; | Structure Information | Remaining design life (while performing intended function); | Record added by:
Seabird | Sand nourishment |  | Protect | Approximately 730m3 of sand nourishment | 2023-05-01 | [5 empty] | CW
Seabird | Dune revegetation |  | Protect | Undertaken in conjunction with seawall works | 2016-09-01 | [5 empty] | CW
Seabird | Limestone revetment construction, flex-mat removal |  | Protect | Approximately 700m in length | 2016-07-01 |  | Good condition, potential steepening of the slope since ASCON, ASCON needed to compare |  | Seawall or revetment: Length = 700m, material=limestone; crest level=4m AHD, crest width=3.3m, rock armour =x2 layers of 2-3T | 12yr (estimated) | CW
Seabird | Temporary protection works |  | Protect | Installation of concrete flex-mat and 3500m3 sand nourishment | 2015-07-01 | [5 empty] | CW
Seabird | Sand nourishment Turner Street |  | Protect | Approximately 3500m3 of nourishment | 2015-01-01 | [5 empty] | CW
Seabird | Sand nourishment Turner Street |  | Protect | Approximately 1800m3 of nourishment at Jackson road | 2014-01-01 | [5 empty] | CW
Seabird | Sand nourishment Turner Street |  | Protect | Approximately 2000m3 of sand nourishment, emergency foreshore protection | 2002-10-07 | [5 empty] | CW

## C.Y. Oconnor
|  | Department of Transport C.Y. O'Connor Database of Coastal Management History Date Populated: 01/08/2024 Last Updated: 21/11/2025 |  |  |  | 5 = Good condition, fully functional 3 = Moderate condition, still functional 1 = Poor condition, not functional |  |  | Offshore breakwater: Length, material (rock/GSC), distance to shore, spacing/interval; crest level (rock/GSC), distance to shore, spacing/interval; crest level Groyne: Length, material (rock/GSC/timber), spacing/interval; crest level Seawall or revetment: Length, material (rock/GSC); crest level
Site | Name | Ownership | Mgmt Hierarchy | Description | Year of Construction (completion) | Current Condition | Condition Comments | Past damage/repairs/improvements; | Structure Information (see above) | Remaining design life (while performing intended function); | Record added by:
CY Oconnor Beach North | Engineered fringing reef |  |  | 135 additional concrete modules installed (doubling the original amount) - 3 new rows of 3.5t bombora modules adjacent to current reef structure, shoreside of original structure | 2024-12-01 | [5 empty] | IU
CY Oconnor Beach South | Sand nourishment |  |  | 17 675 m3 of sand sourced from Chelydra Beach | 2024-03-01 | [5 empty] | CW
CY Oconnor Beach North | Reconstruction of dual use path |  |  | 40 m bend section of dual use pathway (north of Catherine Point) relocated inland, straight section | 2023-12-01 | [5 empty] | CW
CY Oconnor Beach North | Sand nourishment |  |  | 6 750 m3 of sand sourced from Island St Groyne | 2023-07-01 | [5 empty] | CW
CY Oconnor Beach North | Geotextile Sand Container revetment |  |  | North wall construction | 2022-01-01 | n/a (buried) |  |  | Crest Level = ~3.3m CD, GSC size = 1.2m3, length = 51m | 3 | CW
CY Oconnor Beach North | Sand nourishment |  |  | 1 500 m3 of sand sourced from Island Street Groyne | 2021-12-01 | [5 empty] | CW
CY Oconnor Beach North | Engineered fringing reef |  |  | Installation of a modular engineered fringing reef comprising a 100 m long, curved section of bespoke concrete armour units in three rows was fabricated and installed by Subcon for the City. Required 105 concrete bombora units. | 2021-12-01 |  |  |  | Crest Level = ~3.8m CD, GSC size = 1.2m3, length = 20m |  | CW
CY Oconnor Beach North | Sand nourishment |  |  | 4 386 m3 of sand sourced from Island St Groyne and haulage south along the beach to the nourishment site. | 2020-12-01 | [5 empty] | CW
CY Oconnor Beach South | Sand nourishment |  |  | 4 956 m3 of sand sourced from Chelydra Beach (involving excavation of sand from the sand trap (Power Station) beach north of Port Coogee and haulage north along the beach to the nourishment site) | 2020-11-01 | [5 empty] | CW
CY Oconnor Beach North | Sand nourishment |  |  | 600 m3 of sand sourced from C.Y. O'Connor Beach North was used to nourish North of Catherine Point Groyne (Small-scale emergency sand nourishment actions were undertaken to in response to severe scarping at the base of the groyne to address public safety issues and protect the base of the groyne) | 2020-02-01 | [5 empty] | CW
CY Oconnor Beach North | Geotextile Sand Container revetment |  |  | South wall construction | 2020-01-01 | [5 empty] | CW
CY Oconnor Beach South | Sand nourishment |  |  | 15000 m3 of sand sourced from Chelydra Beach | 2019-11-01 | [5 empty] | CW
CY Oconnor Beach South | Sand nourishment |  |  | 4500 m3 of sand sourced from Chelydra Beach | 2018-09-01 | [5 empty] | CW
CY Oconnor Beach North | Sand nourishment |  |  | 15 750 m3 of sand sourced from Chelydra Beach (sand back-passing from the power station sand trap) | 2018-08-01 | [5 empty] | CW
CY Oconnor Beach South | Sand nourishment |  |  | 21000 m3 of sand sourced from Chelydra Beach (campaign halved before/after winter) | 2016-10-01 | [5 empty] | CW
CY Oconnor Beach South | Sand nourishment |  |  | 21001 m3 of sand sourced from Chelydra Beach (campaign halved before/after winter) | 2016-05-01 | [5 empty] | CW
CY Oconnor Beach North | Reconstruction of dual use path |  |  | Reconstruction/retreat of the dual-use shared path running along the coast - reconstructed further inland in 2013 (north of the Catherine Point) in response to shoreline recession. | 2013-01-01 | [5 empty] | CW
Catherine Point | Groyne remediation and extension |  |  | Groyne extension by 30m and access upgrades | 2012-03-01 | 4 |  |  | Crest Level = ~5.25m CD, Armour size 4T, length = 160m |  | CW
CY Oconnor Beach South | Reconstruction of dual use path |  |  | Reconstruction/retreat of the dual-use shared path running along the coast - reconstructed further inland in 2009 (south of Catherine Point) in response to shoreline recession. | 2009-01-01 | [5 empty] | CW
CY Oconnor Beach South | Breakwaters at Port Coogee |  |  | Construction of breakwaters at Port Coogee | 2006-01-02 | [5 empty] | CW
Island Point | Rock revetment |  |  | Rock revetment protection placed on south side of the groyne | 2006-01-01 | [5 empty] | CW
Island Point | Groyne Extension |  |  | Groyne extended 80 m | 1996-01-01 | [5 empty] | CW
Island Point | Groyne Construction |  |  | Initial groyne construction of 107m length | 1962-01-01 | [5 empty] | CW
Catherine Point | Groyne Extension |  |  | Groyne extended 60 m due to saturation | 1962-01-01 | [5 empty] | CW
Catherine Point | Groyne Construction |  |  | Initial groyne construction of 70 m length | 1959-01-01 | [5 empty] | CW
Success Bank | Channel Dredging |  |  | Offshore placement of dredge material to the west of the navigation channel (side-casting) during construction of Success Channel (1942-1945) | 1942-01-01 | [5 empty] | CW

## Kwinana Industrial
|  | Department of Transport Kwinana Industrial Database of Coastal Management History Date Populated: 01/05/2025 Last Updated: 01/05/2025 |  |  |  |  | 5 = Good condition, fully functional 3 = Moderate condition, still functional 1 = Poor condition, not functional |  |  | Offshore breakwater: Length, material (rock/GSC), distance to shore, spacing/interval; crest level (rock/GSC), distance to shore, spacing/interval; crest level Groyne: Length, material (rock/GSC/timber), spacing/interval; crest level Seawall or revetment: Length, material (rock/GSC); crest level
Site | Name | Ownership | Mgmt Hierarchy | Lat | Lon | Year of Construction (completion) | Current Condition | Condition Comments | Past damage/repairs/improvements; | Structure Information | Remaining design life (while performing intended function); | Record added by:
Kwinana Industrial | Revegation works - Challenger Beach |  |  |  |  | 2023-01-01 | [5 empty] | CW
Kwinana Industrial | Revegation works - Challenger Beach |  |  |  |  | 2022-01-01 | [5 empty] | CW
Kwinana Industrial | Revegation works - Watercorp/Suez beaches |  |  |  |  | 2022-01-01 | [5 empty] | CW
Kwinana Industrial | BHP Jetty - partial demolition |  |  |  |  | 2021-01-01 | [5 empty] | CW
Kwinana Industrial | Revegation works - Challenger Beach |  |  |  |  | 2021-01-01 | [5 empty] | CW
Kwinana Industrial | Kwinana Bulk Terminals - revetment |  |  |  |  | 2013-01-01 | [5 empty] | CW
Kwinana Industrial | Kwinana Bulk Jetty - northern revetment |  |  |  |  | 2008-02-01 | [5 empty] | CW
Kwinana Industrial | Challenger Beach revetment (DoT ID S12) |  |  |  |  | 2000-01-01 | 3.25 |  |  |  |  | CW
Kwinana Industrial | BP Headland 1 |  |  |  |  | 1970-01-01 | 2.25 |  |  |  |  | CW
Kwinana Industrial | BP Headland 2 |  |  |  |  | 1970-01-01 | 2.25 |  |  |  |  | CW
Kwinana Industrial | BP Headland 3 |  |  |  |  | 1970-01-01 | 2.25 |  |  |  |  | CW
Kwinana Industrial | BP Headland 4 |  |  |  |  | 1970-01-01 | 2.25 |  |  |  |  | CW
Kwinana Industrial | BP Headland 5 |  |  |  |  | 1970-01-01 | 2 |  |  |  |  | CW
Kwinana Industrial | BP Headland 6 |  |  |  |  | 1970-01-01 | 2 |  |  |  |  | CW
Kwinana Industrial | BP Headland 7 |  |  |  |  | 1970-01-01 | 2 |  |  |  |  | CW
Kwinana Industrial | Kwinana Power Station seawall

## Kwinana Town Beach
|  | Department of Transport Kwinana Town Beach Database of Coastal Management History Date Populated: 01/02/2025 Last Updated: 21/11/2025 | [5 empty] | 5 = Good condition, fully functional 3 = Moderate condition, still functional 1 = Poor condition, not functional |  |  | Offshore breakwater: Length, material (rock/GSC), distance to shore, spacing/interval; crest level (rock/GSC), distance to shore, spacing/interval; crest level Groyne: Length, material (rock/GSC/timber), spacing/interval; crest level Seawall or revetment: Length, material (rock/GSC); crest level
Site | Name | Ownership | Mgmt Hierarchy | Description | Lat | Lon | Year of Construction (completion) | Current Condition | Condition Comments | Past damage/repairs/improvements; | Structure Information | Remaining design life (while performing intended function); | Record added by:
Kwinana | 3191m3 sand nourishment - headland |  | Protect | Sand nourishment via trucking undertaken by City of Rockingham from Point Peron Sand trap |  |  | 2024-11-01 | [5 empty] | CW
Kwinana | 14584m3 sand nourishment - headland |  | Protect | Sand nourishment via trucking undertaken by City of Rockingham from Point Peron Sand trap |  |  | 2021-02-01 | [5 empty] | CW
Kwinana | 14503m3 sand nourishment - headland |  | Protect | Sand nourishment via trucking undertaken by City of Rockingham from Point Peron Sand trap |  |  | 2019-11-19 | [5 empty] | IU/LR
Kwinana | 14000m3 sand nourishment - headland |  | Protect | Sand nourishment via trucking undertaken by City of Rockingham from Point Peron Sand trap |  |  | 2019-05-23 | [5 empty] | IU/LR
Kwinana | 13500m3 sand nourishment - headland |  | Protect | Sand nourishment via trucking undertaken by City of Rockingham from Point Peron Sand trap |  |  | 2012-03-09 | [5 empty] | CW
Kwinana | 6600m3 sand nourishment - headland |  | Protect | Sand nourishment via trucking undertaken by City of Rockingham from Point Peron Sand trap |  |  | 2008-02-01 | [5 empty] | CW
Kwinana | Initial construction of southern artificial headland |  | Protect | Initial construction estimated |  |  | 2007-07-01 | 3.25 | Condition - functioning |  | 50m x 20m, limestone, 3-5T external armour, 1-3T internal armour, crest 2.35m CD |  | CW
Kwinana | Initial construction of northern artificial headland |  | Protect | Initial construction estimated |  |  | 2007-07-01 | 3.25 | Condition - functioning |  | 50m x 20m, limestone, 3-5T external armour, 1-3T internal armour, crest 2.35m CD |  | CW
Kwinana | 10000m3 sand nourishment - south Wells Park |  | Protect | Sand nourishment undertaken by City of Rockingham building out the dune, 500m south of the Well Park wreck |  |  | 2003-07-01 | [5 empty] | CW
Kwinana | 11500m3 sand nourishment - south Wells Park |  | Protect | Sand nourishment undertaken by City of Rockingham building out the dune, 500m south of the Well Park wreck |  |  | 2003-01-01 | [5 empty] | CW
Kwinana | 4650m3 sand nourishment - south Wells Park |  | Protect | Sand nourishment undertaken by City of Rockingham building out the dune, 500m south of the Well Park wreck |  |  | 2001-10-01 | [5 empty] | CW
Kwinana | Rubble mound revetment extension |  | Protect | Extension of southern end of rubble mound revetment south of Wells Park |  |  | 1997-01-01 | 2 | Exposed core, poorly interlocked armour units, and minimal crest width |  | Crest estimated in 2012, 1.5-2.0m AHD | N/A | CW
Kwinana | Rubble mound revetment construction |  | Protect | Initial construction |  |  | 1981-01-01 | 2 | Exposed core, poorly interlocked armour units, and minimal crest width |  | Varied crest height estimated in 2012, 3.2m AHD at northern end, 1.6m AHD at 110m south of Wells Park. | N/A | CW
Kwinana | Limestone retaining wall construction |  | Protect | Initial construction |  |  | 1978-01-01 | 2 | Rotation and cracking |  |  |  | CW

## Rockingham Townsite
|  | Department of Transport Rockingham Townsite Database of Coastal Management History Date populated: 01/02/2025 Last updated: 01/02/2025 | [5 empty] | 5 = Good condition, fully functional 3 = Moderate condition, still functional 1 = Poor condition, not functional |  |  | Offshore breakwater: Length, material (rock/GSC), distance to shore, spacing/interval; crest level (rock/GSC), distance to shore, spacing/interval; crest level Groyne: Length, material (rock/GSC/timber), spacing/interval; crest level Seawall or revetment: Length, material (rock/GSC); crest level
Site | Name | Ownership | Mgmt Hierarchy | Description | Lat | Lon | Year of Construction (completion) | Current Condition | Condition Comments | Past damage/repairs/improvements; | Structure Information | Remaining design life (while performing intended function); | Record added by:
Rockingham Townsite | Sand nourishment - Proposed |  | Protect | Hymus street seawall |  |  | 2024-09-01 |  |  |  | Informal rubble mound revetment |  | CW
Rockingham Townsite | Sand Nourishment |  | Protect | 3000m3 nourished at Palm beach west boat ramp to Hymus St |  |  | 2022-10-22 | [5 empty] | CW
Rockingham Townsite | Sand Nourishment |  | Protect | 1773m3 nourished at Palm beach west boat ramp to Hymus St |  |  | 2021-10-01 | [5 empty] | CW
Rockingham Townsite | Rockingham foreshore redevelopment |  | Protect | Rockingham Foreshore Beach Plaza Redevelopment Project , including seawall construction and scour protection at the toe of the reinforced concrete seawall. Estimated 700 GSC's |  |  | 2019-09-01 | [5 empty] | CW
Rockingham Townsite | Sand Nourishment |  | Protect | 200m3 nourished at Mangles Bay Fishing Club |  |  | 2015-08-12 | [5 empty] | CW
Rockingham Townsite | Construction of Val Street Seawall and scour protection (apart of jetty) |  | Protect | Construction of Val Street Jetty 0-100m Jetty Approach Section. Demolition of existing approach and old jetty head. Onshore Reconstituted Limestone Seawall and Construction and Scour Protection Works. 213 GSCs |  |  | 2015-03-01 | [5 empty] | CW
Rockingham Townsite | Sand Nourishment |  | Protect | 400m3 nourished at Mangles Bay Fishing Club |  |  | 2015-01-01 | [5 empty] | CW
Rockingham Townsite | Sand Nourishment |  | Protect | 2000m3 nourished at Flinders lane to Wanliss St |  |  | 2014-08-08 | [5 empty] | CW
Rockingham Townsite | Sand Nourishment |  | Protect | 1000m3 nourished at Victoria St Car Park |  |  | 2013-01-16 | [5 empty] | CW
Rockingham Townsite | Sand Nourishment |  | Protect | 1000m3 nourished at Victoria St Car Park |  |  | 2012-11-08 | [5 empty] | CW
Rockingham Townsite | Informal rock placement at Mangles Bay Fishing Club |  | Protect | Rock placement up western end of coastline. (Evidenced from aerial imagery) |  |  | 2012-01-01 | [5 empty] | CW
Rockingham Townsite | Sand Nourishment |  | Protect | 4500m3 nourished at Palm beach west boat ramp to Hymus St |  |  | 2011-07-18 | [5 empty] | CW
Rockingham Townsite | Sand Nourishment |  | Protect | 1500m3 nourished at Hymus St beach |  |  | 2011-07-11 | [5 empty] | CW
Rockingham Townsite | Sand Nourishment |  | Protect | 4000m3 nourished at Wanliss St beach |  |  | 2011-06-30 | [5 empty] | CW
Rockingham Townsite | Sand Nourishment |  | Protect | 1500m3 nourished at Hymus St beach |  |  | 2011-05-21 | [5 empty] | CW
Rockingham Townsite | Sand Nourishment |  | Protect | 1500m3 nourished at Hymus St beach |  |  | 2010-04-09 | [5 empty] | CW
Rockingham Townsite | Sand Nourishment |  | Protect | 1000m3 nourished at Victoria St Car Park beach |  |  | 2010-01-29 | [5 empty] | CW
Rockingham Townsite | Palm Beach Seawall and scour protection (apart of jetty) |  | Protect | Limestone Seawall; 350mm x 350mm x 1000mm Reconstituted Limestone Blocks, with x251 0.75m3 Elco Rock Geotextile Sand Containers; Bidim A34 Geotextile. Includes Tensar SS20 Biaaxial Geogrid landside of seawall. Base of wall 1.3m below NSL. |  |  | 2009-08-10 | [5 empty] | CW
Rockingham Townsite | Geotextile sand container revetment (Flinders lane) |  | Protect | GSC revetment installed either side of limestone lookout. Local beach sand use for backfill over scour protection |  |  | 2004-01-01 | [5 empty] | CW
Rockingham Townsite | Timber groynes construction |  | Protect | 30m Timber Groyne (Jarrah) constructed 67m east of cnr Hymus St/The Esplanade at Palm Beach Foreshore. A second Jarrah Groyne (27m) is constructed within the Palm Beach West Boat Ramp structure, located 380m east of the western groyne. The groynes have helped stabilised the Palm Beach Foreshore beach compartment. |  |  | 2000-01-01 | [5 empty] | CW
Rockingham Townsite | Informal limestone revetment construction |  | Protect | Informal limestone revetment armouring footpath and road bend at Hymus street |  |  | 2000-01-01 | [5 empty] | CW

## North Point Peron
|  | Department of Transport North Point Peron Database of Coastal Management History Date populated: 01/02/2025 Last Updated: 15/06/2026 | [5 empty] | 5 = Good condition, fully functional 3 = Moderate condition, still functional 1 = Poor condition, not functional |  |  | Offshore breakwater: Length, material (rock/GSC), distance to shore, spacing/interval; crest level (rock/GSC), distance to shore, spacing/interval; crest level Groyne: Length, material (rock/GSC/timber), spacing/interval; crest level Seawall or revetment: Length, material (rock/GSC); crest level
Site | Name | Ownership | Mgmt Hierarchy | Description | Lat | Lon | Year of Construction (completion) | Current Condition | Condition Comments | Past damage/repairs/improvements; | Structure Information | Remaining design life (while performing intended function); | Record added by:
North Point Peron | Sand backpassing/nourishment |  | Protect | 1500m3 stabilisation works on eastern side of GSC groyne |  |  | 2024-10-24 | [5 empty] | Updated/checked by LR
North Point Peron | Sand Trap Scraping & Stockpiling |  | Protect | Estimated 12000m3 scraped and stockpiled in sandtrap and used for CoR nourishment (removed from the system) |  |  | 2024-01-01 | [5 empty] | Updated/checked by LR
North Point Peron | Sand Trap Scraping & Stockpiling |  | Protect | Estimated 5000m3 scraped and stockpiled in sandtrap and used for CoR nourishment (removed from the system) |  |  | 2023-09-13 | [5 empty] | Updated/checked by LR
North Point Peron | Spur groyne extension and breakwater upgrade |  | Protect | Extension and upgrade to spur groyne, upgrade to breakwater/revetment |  |  | 2022-06-01 |  |  |  | Spur groyne 75m, BW and revetemnet 125m. Crest = 4.25m CD, Limestone, W50 = 4T | 48 | CW
North Point Peron | Rock seawall upgrade (DBCA) |  | Protect | Reconfigured rock seawall, and upgrade/widening of dual use pathway |  |  | 2022-01-01 | 4.75 | Very good condition, well built (recently upgraded) |  |  |  | CW
North Point Peron | Sand Trap Scraping & Stockpiling |  | Protect | Estimated 15000m3 scraped and stockpiled in sandtrap and used for CoR nourishment (removed from the system) |  |  | 2022-01-01 | [5 empty] | Updated/checked by LR
North Point Peron | GSC revetment installation |  | Protect | Estimated 50m length, understood to be installed by Camp School, using Neo Civil 2.5m3 GSCs |  |  | 2021-08-01 |  | Buried, satelite imagery shows eaternmost bags may be damaged from vehicle accessing beach through gate |  |  |  | CW
North Point Peron | Sand Trap Scraping & Stockpiling |  | Protect | Estimated 22000m3 scraped and stockpiled in sandtrap and used for CoR nourishment (removed from the system) |  |  | 2021-01-01 | [5 empty] | Updated/checked by LR
North Point Peron | Sand Trap Scraping & Stockpiling |  | Protect | Estimated 16000m3 scraped and stockpiled in sandtrap and used for CoR nourishment (removed from the system) |  |  | 2020-01-01 | [5 empty] | Updated/checked by LR
North Point Peron | Sand Trap Scraping & Stockpiling |  | Protect | Estimated 15000m3 scraped and stockpiled in sandtrap and used for CoR nourishment (removed from the system) |  |  | 2019-01-01 | [5 empty] | Updated/checked by LR
North Point Peron | Sand Trap Scraping & Stockpiling |  | Protect | Estimated 20000m3 scraped and stockpiled in sandtrap and used for CoR nourishment (removed from the system) |  |  | 2018-01-01 | [5 empty] | Updated/checked by LR
North Point Peron | Sand Trap Scraping & Stockpiling |  | Protect | Estimated 19000m3 scraped and stockpiled in sandtrap and used for CoR nourishment (removed from the system) |  |  | 2017-01-01 | [5 empty] | Updated/checked by LR
North Point Peron | Sand Trap Scraping & Stockpiling |  | Protect | Estimated 12000m3 scraped and stockpiled in sandtrap and used for CoR nourishment (removed from the system) |  |  | 2016-01-01 | [5 empty] | Updated/checked by LR
North Point Peron | Sand Trap Scraping & Stockpiling |  | Protect | Estimated 10500m3 scraped and stockpiled in sandtrap and used for CoR nourishment (removed from the system) |  |  | 2015-01-01 | [5 empty] | Updated/checked by LR
North Point Peron | Sand backpassing/nourishment |  | Protect | 4500m3 to reinstsate of beach profile between Pt. Peron Limestone Seawall, east to the Point Peron Education Camp School. |  |  | 2014-04-01 | [5 empty] | Updated/checked by LR
North Point Peron | Sand Trap Scraping & Stockpiling |  | Protect | Estimated 21000m3 scraped and stockpiled in sandtrap and used for CoR nourishment (removed from the system) |  |  | 2014-01-01 | [5 empty] | Updated/checked by LR
North Point Peron | Sand Nourishment - west of GSC groyne |  | Protect | Estimated 12000m3 nourishment for establishment of new beach profile on the western compartment adjacent to the new 61m long Geotextile Sand Container Groyne |  |  | 2013-05-29 | [5 empty] | Updated/checked by LR
North Point Peron | Sand Trap Scraping & Stockpiling |  | Protect | Estimated 15000m3 removed from sand trap |  |  | 2013-05-20 | [5 empty] | Updated/checked by LR
North Point Peron | Sand Nourishment - west of camp school |  | Protect | Estimated 1000m3 nourishment to reinstate beach adjacent to Pt.Peron Camp School |  |  | 2013-03-12 | [5 empty] | Updated/checked by LR
North Point Peron | GSC groyne installation |  | Protect | Constructed at eastern side of School Camp foreshore |  |  | 2013-01-01 | 1.67 | Bags slumping and rips apparent, due for replacement |  | 61m length, trunk ~1.5m AHD, head ~0.9m AHD, Up to 4 layers of 2.5m3 bags (3m3 bags) 2.5m3 Geotextile Sand Containers; 197 xDouble Sided Vandal Deterrent GSCs; 43xDouble Sided Vandal Deterrent Scour Flap Long Edge GSC's; 11xDouble Sided Vandal Deterrent Scour Flap Short Edge GSC's. | 0 | CW
North Point Peron | Sand Trap Scraping & Stockpiling |  |  | Estimated 15000m3 scraped and stockpiled in sandtrap and used for CoR nourishment (removed from the system) and used for CoR nourishment (removed from the system) |  |  | 2013-01-01 | [5 empty] | CW
North Point Peron | Sand Trap Excavation |  | Protect | Estimated 10000m3 removed from sand trap |  |  | 2012-12-07 | [5 empty] | Updated/checked by LR
North Point Peron | Sand Trap Excavation |  | Protect | Estimated 5000m3 removed from sand trap |  |  | 2012-06-28 | [5 empty] | Updated/checked by LR
North Point Peron | Sand Trap Excavation |  | Protect | Estimated 10000m3 removed from sand trap |  |  | 2011-09-23 | [5 empty] | Updated/checked by LR
North Point Peron | Sand Trap Excavation |  | Protect | Estimated 5000m3 removed from sand trap |  |  | 2010-09-24 | [5 empty] | Updated/checked by LR
North Point Peron | Sand Trap Excavation |  | Protect | Estimated 5000m3 removed from sand trap |  |  | 2009-12-07 | [5 empty] | Updated/checked by LR
North Point Peron | Sand Trap Excavation |  | Protect | Estimated 12000m3 removed from sand trap |  |  | 2009-09-18 | [5 empty] | Updated/checked by LR
North Point Peron | Sand Trap Excavation |  | Protect | Estimated 5000m3 removed from sand trap |  |  | 2009-02-13 | [5 empty] | Updated/checked by LR
North Point Peron | Sand Trap Excavation |  | Protect | Estimated 5000m3 removed from sand trap |  |  | 2009-01-19 | [5 empty] | Updated/checked by LR
North Point Peron | Sand Trap Excavation |  | Protect | Estimated 12000m3 removed from sand trap |  |  | 2008-11-07 | [5 empty] | Updated/checked by LR
North Point Peron | Sand Trap Excavation |  | Protect | Estimated 12000m3 removed from sand trap |  |  | 2007-01-01 | [5 empty] | Updated/checked by LR
North Point Peron | Sand Trap Excavation |  | Protect | Estimated 10000m3 removed from sand trap |  |  | 2006-01-01 | [5 empty] | Updated/checked by LR
North Point Peron | Sand Trap Excavation |  | Protect | Unknown m3 removed from sand trap |  |  | 2005-01-01 | [5 empty] | Updated/checked by LR
North Point Peron | Sand Trap Excavation |  | Protect | Estimated 9000m3 removed from sand trap |  |  | 2004-01-01 | [5 empty] | Updated/checked by LR
North Point Peron | Sand Trap Excavation |  | Protect | Estimated 11000m3 removed from sand trap |  |  | 2003-01-01 | [5 empty] | Updated/checked by LR
North Point Peron | Sand Trap Excavation |  | Protect | Estimated 11000m3 removed from sand trap |  |  | 2002-01-01 | [5 empty] | Updated/checked by LR
North Point Peron | Sand Trap Excavation |  | Protect | Estimated 11000m3 removed from sand trap |  |  | 2001-01-01 | [5 empty] | Updated/checked by LR
North Point Peron | Sand Trap Excavation |  | Protect | Estimated 11000m3 removed from sand trap |  |  | 2000-01-01 | [5 empty] | Updated/checked by LR
North Point Peron | Spur extension to sand trap groyne |  | Protect | Spur groyne added northwards ~50m |  |  | 1990-01-01 | [5 empty] | Updated/checked by LR
North Point Peron | Rock seawall |  | Protect | Seawall built by DEC protecting path access, ~170m long |  |  | 1988-01-01
North Point Peron | Extension to sand trap groyne |  | Protect | 90 degree, ~65m extension to sand trap groyne eastwards |  |  | 1986-01-01
North Point Peron | Original sand trap groyne |  | Protect | Original construction west of causeway abutment, ~200m |  |  | 1973-01-01
North Point Peron | Original boat launch construction |  | Protect | Boat launching facility and straight groyne |  |  | 1973-01-01

## Mandurah Northern Beaches
|  | Department of Transport Mandurah Northern Beaches Database of Coastal Management History Date Populated: 01/10/2024 Last Updated: 21/11/2025 | [5 empty] | 5 = Good condition, fully functional 3 = Moderate condition, still functional 1 = Poor condition, not functional |  |  | Offshore breakwater: Length, material (rock/GSC), distance to shore, spacing/interval; crest level (rock/GSC), distance to shore, spacing/interval; crest level Groyne: Length, material (rock/GSC/timber), spacing/interval; crest level Seawall or revetment: Length, material (rock/GSC); crest level
Site | Name | Ownership | Mgmt Hierarchy | Description | Lat | Lon | Year of Construction (completion) | Current Condition (/5) | Condition Comments | Past damage/repairs/improvements; | Structure Information (see above) | Remaining design life (while performing intended function); | Record added by:
Mandurah Northern Beaches | Sand Bypassing |  |  | 175330 m 3 pumped sand bypassing from Doddi's beach sandtrap |  |  | 2025-11-01 | [5 empty] | IU
Mandurah Northern Beaches | Sand Bypassing |  |  | 156711 m3 pumped sand bypassing from Doddi's beach sandtrap |  |  | 2024-11-01 | [5 empty] | IU
Mandurah Northern Beaches | Sand Bypassing |  |  | 180577 m3 pumped sand bypassing from Doddi's beach sandtrap |  |  | 2023-11-01 | [5 empty] | CW
Mandurah Northern Beaches | Sand Bypassing |  |  | 181329 m3 pumped sand bypassing from Doddi's beach sandtrap |  |  | 2022-11-01 | [5 empty] | CW
Mandurah Northern Beaches | Sand Bypassing |  |  | 220003 m3 pumped sand bypassing from Doddi's beach sandtrap |  |  | 2021-11-01 | [5 empty] | CW
Mandurah Northern Beaches | Sand Bypassing |  |  | 191659 m3 pumped sand bypassing from Doddi's beach sandtrap |  |  | 2020-11-01 | [5 empty] | CW
Mandurah Northern Beaches | Sand Bypassing |  |  | 160000 m3 pumped sand bypassing from Doddi's beach sandtrap |  |  | 2019-11-01 | [5 empty] | CW
Mandurah Northern Beaches | Sand nourishment/scraping |  |  | Fifth groyne (San Remo) sand scraped from adjacent to groyne and used to protect scarped dune crest extending approximately 430m long south of the groyne |  |  | 2019-01-01 | [5 empty] | CW
Mandurah Northern Beaches | Sand Bypassing |  |  | 170000 m3 pumped sand bypassing from Doddi's beach sandtrap |  |  | 2018-11-01 | [5 empty] | CW
Mandurah Northern Beaches | Sand Bypassing |  |  | 175007 m3 pumped sand bypassing from Doddi's beach sandtrap |  |  | 2017-11-01 | [5 empty] | CW
Mandurah Northern Beaches | Sand Bypassing |  |  | 166600 m3 pumped sand bypassing from Doddi's beach sandtrap |  |  | 2016-11-01 | [5 empty] | CW
Mandurah Northern Beaches | Sand Bypassing |  |  | 196400 m3 pumped sand bypassing from Doddi's beach sandtrap |  |  | 2015-11-01 | [5 empty] | CW
Mandurah Northern Beaches | Sand Bypassing |  |  | 149930 m3 pumped sand bypassing from Doddi's beach sandtrap |  |  | 2014-11-01 | [5 empty] | CW
Mandurah Northern Beaches | Sand Bypassing |  |  | 133000 m3 pumped sand bypassing from Doddi's beach sandtrap |  |  | 2013-11-01 | [5 empty] | CW
Mandurah Northern Beaches | Sand Bypassing |  |  | 150043 m3 pumped sand bypassing from Doddi's beach sandtrap |  |  | 2012-11-01 | [5 empty] | CW
Mandurah Northern Beaches | Sand Bypassing |  |  | 130409 m3 pumped sand bypassing from Doddi's beach sandtrap |  |  | 2011-11-01 | [5 empty] | CW
Mandurah Northern Beaches | Groyne maintenance/reconfiguration |  |  | Fourth groyne (Wade St) reconfiguration, some armour on neck of groyne moved to protect the northern abutment. Lowering of neck intentional to encourage sand movement in high water events |  |  | 2011-01-01 | 3 | Slumping/scattered armour |  |  | N/A (Dependant on sand management) | CW
Mandurah Northern Beaches | Sand Bypassing |  |  | 101886 m3 pumped sand bypassing from Doddi's beach sandtrap |  |  | 2010-11-01 | [5 empty] | CW
Mandurah Northern Beaches | Sand Bypassing |  |  | 112129 m3 pumped sand bypassing from Doddi's beach sandtrap |  |  | 2009-11-01 | [5 empty] | CW
Mandurah Northern Beaches | Sand nourishment |  |  | Fourth groyne (Wade St), unknown qty/source |  |  | 2009-01-01 | [5 empty] | CW
Mandurah Northern Beaches | Groyne maintenance |  |  | Fifth groyne (San Remo) Approximately 12 large rocks worked into existing voids in groyne. |  |  | 2009-01-01 | 5 |  |  |  |  | CW
Mandurah Northern Beaches | Sand Bypassing |  |  | 164278 m3 pumped sand bypassing from Doddi's beach sandtrap |  |  | 2008-11-01 | [5 empty] | CW
Mandurah Northern Beaches | Sand Bypassing |  |  | 120000 m3 pumped sand bypassing from Doddi's beach sandtrap |  |  | 2007-11-01 | [5 empty] | CW
Mandurah Northern Beaches | Sand nourishment |  |  | 5000m3 or nourishment at Second groyne (Henson St) sourced from Doddis sand trap - |  |  | 2007-03-01 | [5 empty] | CW
Mandurah Northern Beaches | Sand nourishment |  |  | Remedial sand nourishment at Fourth groyne (Wade St). Unknown volume |  |  | 2007-01-01 | [5 empty] | CW
Mandurah Northern Beaches | Sand Bypassing |  |  | 74000 m3 pumped sand bypassing from Doddi's beach sandtrap |  |  | 2006-11-01 | [5 empty] | CW
Mandurah Northern Beaches | Sand Bypassing |  |  | 100000 m3 pumped sand bypassing from Doddi's beach sandtrap |  |  | 2005-11-01 | [5 empty] | CW
Mandurah Northern Beaches | Groyne construction |  |  | Fifth groyne (San Remo) construction |  |  | 2005-01-01 | 5 |  |  | Length=50m, limestone armour, 4-8T armour,crest level 4.6m CD (3.841m) |  | CW
Mandurah Northern Beaches | Sand nourishment |  |  | Approximately 50000m3 nourishment to accompany Fifth groyne construction |  |  | 2005-01-01 | [5 empty] | CW
Mandurah Northern Beaches | Sand Bypassing |  |  | 99000 m3 pumped sand bypassing from Doddi's beach sandtrap |  |  | 2004-11-01 | [5 empty] | CW
Mandurah Northern Beaches | Groyne repairs |  | Protect | Minor repairs to Fourth groyne, replacement of rocks along the length of the trunk and head |  |  | 2004-01-01 | 3 | Slumping/scattered armour |  | Length = 65m, limestone armour, 2-8T | 20 | CW
Mandurah Northern Beaches | Groyne repairs |  | Protect | Minor repairs to Third groyne, replacement of rocks along the length of the trunk and head |  |  | 2004-01-01 | 3 | Some slumping/moderate interlocking |  | Length = 40m, limestone armour, 2-8T | 20 | CW
Mandurah Northern Beaches | Groyne repairs |  | Protect | Minor repairs to Second groyne, replacement of rocks along the length of the trunk and head |  |  | 2004-01-01 | 3 | Scattered armour at neck |  | Length = 40m, limestone armour, 2-8T | 20 | CW
Mandurah Northern Beaches | Groyne repairs |  | Protect | Minor repairs to First groyne, replacement of rocks along the length of the trunk and head |  |  | 2004-01-01 | 3 | Scattered armour at neck |  | Length = 60m, limestone armour, 2-8T | 20 | CW
Mandurah Northern Beaches | Sand Bypassing |  |  | 100000 m3 pumped sand bypassing from Doddi's beach sandtrap |  |  | 2003-11-01 | [5 empty] | CW
Mandurah Northern Beaches | Seawall construction |  |  | Town beach seawall upgrade (TABEC). Chainages 180m to 380m |  |  | 2003-01-01 | 3.5 | Armour, rock strength and density all not adequate as per the original design and todays standards, despite this wall still functional, and providing sand buffer exists, repairs not urgent. |  | Length = 360m, limestone armour <1T (MPR estimates) | 5 (providing sand buffer maintained) | CW
Mandurah Northern Beaches | Sand Bypassing |  |  | 100000 m3 pumped sand bypassing from Doddi's beach sandtrap |  |  | 2002-11-01 | [5 empty] | CW
Mandurah Northern Beaches | Sand Bypassing |  |  | 100000 m3 pumped sand bypassing from Doddi's beach sandtrap |  |  | 2001-11-01 | [5 empty] | CW
Mandurah Northern Beaches | Sand Bypassing |  |  | 108000 m3 pumped sand bypassing from Doddi's beach sandtrap |  |  | 2000-11-01 | [5 empty] | CW
Mandurah Northern Beaches | Sand Bypassing |  |  | 112000 m3 pumped sand bypassing from Doddi's beach sandtrap |  |  | 1999-11-01 | [5 empty] | CW
Mandurah Northern Beaches | Sand Bypassing |  |  | 105000 m3 pumped sand bypassing from Doddi's beach sandtrap |  |  | 1998-11-01 | [5 empty] | CW
Mandurah Northern Beaches | Seawall construction |  |  | Town beach seawall construction as part of the Mandurah Ocean Marina development (didn't meet design parameters) |  |  | 1998-01-01 | [5 empty] | CW
Mandurah Northern Beaches | Sand Bypassing |  |  | 58000 m3 pumped sand bypassing from Doddi's beach sandtrap |  |  | 1997-11-01 | [5 empty] | CW
Mandurah Northern Beaches | Sand Bypassing |  |  | 39000 m3 pumped sand bypassing from Doddi's beach sandtrap |  |  | 1996-11-01 | [5 empty] | CW
Mandurah Northern Beaches | Sand Bypassing |  |  | 142000 m3 pumped sand bypassing from Doddi's beach sandtrap (initiation of 5 year contract) |  |  | 1995-11-01 | [5 empty] | CW
Mandurah Northern Beaches | Sand Bypassing |  |  | 26000 m3 pumped sand bypassing from Doddi's beach sandtrap |  |  | 1994-11-01 | [5 empty] | CW
Mandurah Northern Beaches | Sand Bypassing |  |  | 44000 m3 pumped sand bypassing from Doddi's beach sandtrap |  |  | 1993-11-01 | [5 empty] | CW
Mandurah Entrance Channel | Seawall construction |  |  | Eastern seawall construction |  |  | 1975-01-01 | [5 empty] | CW
Mandurah Northern Beaches | Groyne construction |  |  | Fourth groyne (Wade st) construction |  |  | 1975-01-01 | [5 empty] | CW
Mandurah Northern Beaches | Groyne construction |  |  | Third groyne (Orion Rd) construction |  |  | 1975-01-01 | [5 empty] | CW
Mandurah Northern Beaches | Groyne construction |  |  | Second groyne (Henson St) |  |  | 1975-01-01 | [5 empty] | CW
Mandurah Northern Beaches | Groyne construction |  |  | First groyne (Aileen St) |  |  | 1975-01-01 | [5 empty] | CW
Mandurah Entrance Channel | Training wall construction |  |  | Training wall built to define entrance channel west and eastern shores |  |  | 1969-01-01 | [5 empty] | CW

## Wonnerup
|  | Department of Transport Wonnerup Database of Coastal Management History Date Populated: 01/06/2025 Last Updated: 01/06/2025 | [5 empty] | 5 = Good condition, fully functional 3 = Moderate condition, still functional 1 = Poor condition, not functional |  | Offshore breakwater: Length, material (rock/GSC), distance to shore, spacing/interval; crest level (rock/GSC), distance to shore, spacing/interval; crest level Groyne: Length, material (rock/GSC/timber), spacing/interval; crest level Seawall or revetment: Length, material (rock/GSC); crest level
Site | Name | Ownership | Mgmt Hierarchy | Description | Lat | Lon | Year of Construction (completion) | Current Condition | Past damage/repairs/improvements; | Structure Information (see above) | Remaining design life (while performing intended function); | Record added by:
Busselton - Wonnerup | 19799m3 nourishment volume at Wonnerup from PG Dredging disposal | [5 empty] | 2024-12-01 |  |  |  |  | CW
Busselton - Wonnerup | 11360m3 nourishment at Wonnerup from external trucking | [5 empty] | 2024-01-01 |  |  |  |  | CW
Busselton - Wonnerup | 9590m3 nourishment at Wonnerup from external trucking | [5 empty] | 2023-01-01 |  |  |  |  | CW
Busselton - Wonnerup | 12190m3 nourishment at Wonnerup from PG Dredging disposal | [5 empty] | 2023-01-01 |  |  |  |  | CW
Busselton - Wonnerup | 15160m3 nourishment at Wonnerup from external trucking | [5 empty] | 2022-01-01 |  |  |  |  | CW
Busselton - Wonnerup | 13760m3 of nourishment at Wonnerup from PG Dredging disposal | [5 empty] | 2022-01-01 |  |  |  |  | CW
Busselton - Wonnerup | 18700m3 of nourishment at Wonnerup from PG Dredging disposal | [5 empty] | 2021-01-01 |  |  |  |  | CW
Busselton - Wonnerup | 8500m3 of nourishment at Wonnerup from external truckin | [5 empty] | 2021-01-01 |  |  |  |  | CW
Busselton - Wonnerup | Construction of GSC groyne 9 | Built by CoB |  |  |  |  | 2020-01-01 |  |  |  |  | CW
Busselton - Wonnerup | Construction of GSC groyne 10 | Built by CoB |  |  |  |  | 2020-01-01 |  |  |  |  | CW
Busselton - Wonnerup | 11800m3 nourishment volume at Wonnerup from external trucking | [5 empty] | 2020-01-01 |  |  |  |  | CW
Busselton - Wonnerup | 21580m3 nourishment volume at Wonnerup | [5 empty] | 2019-01-01 |  |  |  |  | CW
Busselton - Wonnerup | Groyne 3 refurbishment | [5 empty] | 2019-01-01 | 3 |  | Length 35m. Rock (Ironstone and Granite), Armour: M50 = 2T Ironstone, Crest height 0.5m AHD | 20 | CW
Busselton - Wonnerup | Groyne 4 refurbishment | [5 empty] | 2019-01-01 | 3 |  | Length 35m. Rock (Ironstone and Granite), Armour: M50 = 2T Ironstone, Crest height 0.2m AHD | 20 | CW
Busselton - Wonnerup | Groyne 5 refurbishment | [5 empty] | 2019-01-01 | 3 |  | Length 35m. Rock (Ironstone and Granite), Armour: M50 = 2T Ironstone, Crest height 0.1m AHD | 20 | CW
Busselton - Wonnerup | Groyne 6 refurbishment | [5 empty] | 2019-01-01 | 3 |  | Length 35m. Rock (Ironstone and Granite), Armour: M50 = 2T Ironstone, Crest height 0.0m AHD | 20 | CW
Busselton - Wonnerup | 30291m3 nourishment at Wonnerup from external trucking | [5 empty] | 2018-01-01 |  |  |  |  | CW
Busselton - Wonnerup | 43628m3 nourishment at Wonnerup from external trucking | [5 empty] | 2017-01-01 |  |  |  |  | CW
Busselton - Wonnerup | Construction of GSC groyne 7 | Built by CoB |  | Relatively short (<40m) and low |  |  | 2017-01-01 |  |  |  |  | CW
Busselton - Wonnerup | Construction of GSC groyne 8 | Built by CoB |  | Relatively short (<40m) and low |  |  | 2017-01-01 |  |  |  |  | CW
Busselton - Wonnerup | Groyne 1 refurbishment |  |  | Refurbished by developer (Seaport) based on MRA design |  |  | 2016-01-01 | 2.25 |  | . Rock (Ironstone), Armour: Double layer of M50, 3T Ironstone, Crest height 2.5m AHD, Crest width 3m |  | CW
Busselton - Wonnerup | Groyne 2 refurbishment |  |  | Refurbished by developer (Seaport) based on MRA design |  |  | 2016-01-01 | 2.75 |  | . Rock (Ironstone), Armour: Double layer of M50, 3T Ironstone, Crest height 2.5m AHD, Crest width 3m |  | CW
Busselton - Wonnerup | 10000m3 nourishment at Wonnerup from external trucking | [5 empty] | 2015-01-01 |  |  |  |  | CW
Busselton - Wonnerup | Port Geographe - major groyne and revetment reconfiguration |  |  | Reconfiguration undertaken between Nov2013 to June 2014 |  |  | 2015-01-01 |  |  |  |  | CW
Busselton - Wonnerup | 35000m3 nourishment volume at Wonnerup | [5 empty] | 2014-01-01 |  |  |  |  | CW
Busselton - Wonnerup | Nourishment of ~25000m3 | [5 empty] | 2013-01-01 |  |  |  |  | CW
Busselton - Wonnerup | Nourishment of ~51000m3 | [5 empty] | 2012-01-01 |  |  |  |  | CW
Busselton - Wonnerup | Nourishment of ~45000m3 | [5 empty] | 2011-01-01 |  |  |  |  | CW
Busselton - Wonnerup | Nourishment of ~52400m3 | [5 empty] | 2010-01-01 |  |  |  |  | CW
Busselton - Wonnerup | Nourishment of ~69000m3 | [5 empty] | 2009-01-01 |  |  |  |  | CW
Busselton - Wonnerup | Nourishment of ~124000m3 | [5 empty] | 2008-01-01 |  |  |  |  | CW
Busselton - Wonnerup | Groyne 1 refurbishment |  |  | Refurbished by developer (Seaport) based on MRA design |  |  | 2008-01-01 | 2.25 |  | . Rock (Ironstone), Armour: Double layer of M50, 3T Ironstone, Crest height 2.5m AHD, Crest width 3m |  | CW
Busselton - Wonnerup | Groyne 2 refurbishment |  |  | Refurbished by developer (Seaport) based on MRA design |  |  | 2008-01-01 | 2.75 |  | . Rock (Ironstone), Armour: Double layer of M50, 3T Ironstone, Crest height 2.5m AHD, Crest width 3m |  | CW
Busselton - Wonnerup | Seawall construction | Built by developer |  | Constructed connecting the PG eastern breakwater to the first groyne, a limestone crown wall was also built set-back approximately 20m |  |  | 2007-05-01 |  |  |  |  | CW
Busselton - Wonnerup | Nourishment of ~122000m3 | [5 empty] | 2007-01-01 |  |  |  |  | CW
Busselton - Wonnerup | Initial construction Groyne 1 - laterite ironstone | Built by developer |  |  |  |  | 2006-05-01 |  |  |  |  | CW
Busselton - Wonnerup | Groyne 2 refurbishment | Developer |  |  |  |  | 2006-05-01 |  |  |  |  | CW
Busselton - Wonnerup | Nourishment of 123200m4 | [5 empty] | 2006-01-01 |  |  |  |  | CW
Busselton - Wonnerup | Nourishment of 141234m3 | [5 empty] | 2005-01-01 |  |  |  |  | CW
Busselton - Wonnerup | Nourishment of 98200m3 | [5 empty] | 2004-01-01 |  |  |  |  | CW
Busselton - Wonnerup | Initial construction Groyne 2 - laterite ironstone | Built by developer |  | Low profile ironstone (laterite) groyne |  |  | 2003-01-01 | 2.25 |  | Length 35m. No design details |  | CW
Busselton - Wonnerup | Initial construction Groyne 3 - laterite ironstone | Built by CoB |  | Low profile ironstone (laterite) groyne |  |  | 2003-01-01 | 2.75 |  | Length 35m. No design details |  | CW
Busselton - Wonnerup | Initial construction Groyne 4 - laterite ironstone | Built by CoB |  | Low profile ironstone (laterite) groyne |  |  | 2003-01-01 | 3 |  | Length 35m. No design details |  | CW
Busselton - Wonnerup | Initial construction Groyne 5 - laterite ironstone | Built by CoB |  | Low profile ironstone (laterite) groyne |  |  | 2003-01-01 | 3 |  | Length 35m. No design details |  | CW
Busselton - Wonnerup | Initial construction Groyne 6 - laterite ironstone | Built by CoB |  | Low profile ironstone (laterite) groyne |  |  | 2003-01-01 | 3 |  | Length 35m. No design details |  | CW
Busselton - Wonnerup | Nourishment of 41800m3 | [5 empty] | 2003-01-01 |  |  |  |  | CW
Busselton - Wonnerup | Nourishment of 27825m3 | [5 empty] | 2002-01-01 |  |  |  |  | CW
Busselton - Wonnerup | Construction of Eastern PG Seawall | [5 empty] | 2001-04-01 |  |  |  |  | CW
Busselton - Wonnerup | Nourishment of 18303m6 | [5 empty] | 2001-01-01 |  |  |  |  | CW
Busselton - Wonnerup | Nourishment of 7042m3 | [5 empty] | 2000-01-01 |  |  |  |  | CW
Busselton - Wonnerup | Temporary seawall construction |  |  | Emergency rubble mound seawall constructed to prevent loss of Layman Road |  |  | 1999-07-01 |  |  |  |  | CW
Busselton - Wonnerup | Nourishment of 5000m3 | [5 empty] | 1999-01-01 |  |  |  |  | CW
Busselton - Wonnerup | Nourishment of 82220m3 | [5 empty] | 1998-01-01 |  |  |  |  | CW
Busselton - Wonnerup | Construction of Port Geographe Marina | [5 empty] | 1997-01-01 |  |  |  |  | CW
Busselton - Wonnerup | Nourishment of 77590m3 | [5 empty] | 1996-01-01 |  |  |  |  | CW

## Emu Pt
|  | Department of Transport Emu Point Database of Coastal Management History Date populated: 01/04/2025 Last Updated: 21/11/2025 | [5 empty] | 5 = Good condition, fully functional 3 = Moderate condition, still functional 1 = Poor condition, not functional |  |  | Offshore breakwater: Length, material (rock/GSC), distance to shore, spacing/interval; crest level (rock/GSC), distance to shore, spacing/interval; crest level Groyne: Length, material (rock/GSC/timber), spacing/interval; crest level Seawall or revetment: Length, material (rock/GSC); crest level
Site | Name | Ownership | Mgmt Hierarchy | Description | Lat | Lon | Year of Construction (completion) | Current Condition | Condition Comments | Past damage/repairs/improvements; | Structure Information (see above) | Remaining design life (while performing intended function); | Record added by:
Emu Point | Sand nourishment |  |  | 3,000m3 nourishment to North of Middleton Beach |  |  | 2025-06-26 | [5 empty] | IU
Emu Point | Sand nourishment |  |  | 4,000m3 nourishment to North of Middleton Beach |  |  | 2025-05-23 | [5 empty] | IU
Emu Point | Sand nourishment campaign (sand sourced from Griffiths St Beach) |  |  | 4,500m3 nourishment to Emu Beach + 400m3 over back of revetment |  |  | 2024-12-01 | [5 empty] | IU
Emu Point | Sand nourishment campaign (sand sourced from Griffiths St Beach) | [5 empty] | 2024-04-01 | [5 empty] | CW
Emu Point | Training wall repairs and maintenance |  |  | Reinstatement of laterite rocks to increase the stability and height of the wall, and stabilising backfill with cement to protect it from scouring out when waves wash over the top |  |  | 2014-07-01 | [5 empty] | CW
Emu Point | GSC groyne construction |  |  | Construction of x2 GSC sandbag groynes, initially undertaken as a trial |  |  | 2014-01-01 | [5 empty] | CW
Emu Point | Sand nourishment, 10000m3 (to support GSC groyne trial) |  |  | Sand sourced from Ellen Cove |  |  | 2014-01-01 | [5 empty] | CW
Emu Point | Dual use path relocated (approximate chainage 1050 to 1250m) |  |  | 200m of dual use footpath realignment due to erosion risk |  |  | 2013-01-01 | [5 empty] | CW
Emu Point | GSC revetment construction |  |  | Emergency management measure to avoid relocation of footpath. |  |  | 2011-08-01 | [5 empty] | CW
Emu Point | Revetment extension | [5 empty] | 2011-01-01 | [5 empty] | CW
Emu Point | Revetment extension | [5 empty] | 2005-01-01 | [5 empty] | CW
Emu Point | Revetment extension | [5 empty] | 2001-01-01 | [5 empty] | CW
Emu Point | Emergency revetment | [5 empty] | 1999-01-01 | [5 empty] | CW
Emu Point | Rock headland construction (artificial headland) |  |  | Photo records indicate dredged material used to nourish beach in lee of newly constructed headland |  |  | 1995-01-01 |  |  |  | Headland, 100m length, x2 layers of 1-3T laterite, crest height ~1.5m AHD |  | CW
Emu Point | Groyne extension |  |  | Extended by 20m |  |  | 1995-01-01 | [5 empty] | CW
Emu Point | Beach renourishment, 36000m3 (accompanying headland construction) | [5 empty] | 1995-01-01 | [5 empty] | CW
Emu Point | Revetment extension and Oyster harbour groyne construction | [5 empty] | 1991-01-01 | [5 empty] | CW
Emu Point | Initial groyne construction |  |  | Constructed off Cunningham St. |  |  | 1989-01-01 |  |  |  | ~80m length, laterite rock, x2 layers of 1-3T rock, ~1.95m AHD crest |  | CW
Emu Point | Beach nourishment (accompanying groyne construction) | [5 empty] | 1989-01-01 | [5 empty] | CW
Emu Point | Dredging spoil dumped offshore of Middleton Beach |  |  | Unknown quantity |  |  | 1985-01-01 | [5 empty] | CW
Emu Point | Dredging spoil dumped offshore of Middleton Beach |  |  | Unknown quantity |  |  | 1979-01-01 | [5 empty] | CW
Emu Point | Dredging spoil dumped offshore of Middleton Beach |  |  | Unknown quantity |  |  | 1977-01-01 | [5 empty] | CW
Emu Point | Dredging spoil dumped offshore of Middleton Beach |  |  | Unknown quantity |  |  | 1955-01-01 | [5 empty] | CW
Emu Point | Dredging spoil dumped offshore of Middleton Beach |  |  | Described as 1.53M m3 |  |  | 1925-01-01 | [5 empty] | CW
Emu Point | Dredging spoil dumped offshore of Middleton Beach |  |  | Unknown quantity | [8 empty] | CW
CW
CW
CW
CW
CW
CW
CW
CW
CW
CW
CW
CW
CW
CW
CW
CW
CW
CW
CW
CW
CW
CW
CW
CW
CW
CW
CW
CW
CW
CW

## Data
Name
Ownership
Mgmt Hierarchy
Description
Year of Construction (completion)
Construction Cost Estimate
Current Condition - (Assessment during Site Visit)
Past damage/repairs/improvements;
Design conditions (where previously documented);
Remaining design life (while performing intended function);
Design philosophy/guiding principles (where previously documented);
Intended purpose/function (engineering, amenity/public, environmental);
Benefits/Impacts/issues/challenges/lessons learnt;
Assessment of performance/effectiveness; and
Typical/representative photo/s (captured during the site visit)

## Lists
Site | Name | Ownership | Mgmt Hierarchy | Description | Year of Construction | Construction Cost Estimate | Type of Cost | Current Condition | Past damage/repairs/improvements; | Design conditions (where previously documented); | Remaining design life (while performing intended function); | Design philosophy/guiding principles (where previously documented); | Intended purpose/function (engineering, amenity/public, environmental); | Benefits/Impacts/issues/challenges/lessons learnt; | Assessment of performance/effectiveness; and | Typical/representative photo/s captured during the site visit.
Quinns Beach |  |  | Avoid |  |  |  | Capital
Grannies/Surf Beach |  |  | Retreat |  |  |  | Maintenance
Lancelin |  |  | Accommodate
Seabird |  |  | Protect
CY Oconnor Beach
Kwinana Industrial
Kwinana
Rockingham Townsite
North Point Peron
Mandurah Northern Beaches
Busselton - Wonnerup
Emu Point