Tier 3 Grain Lines

Engineering Review Report

| Revision no. | Date |
| --- | --- |
| Draft v1.0 | 31/07/2020 |
| Draft v2.0 | 17/08/2020 |
| Draft v2.1 | 25/08/2020 |
| Revision 0 | 2/09/2020 |

Agonis Group has prepared this report for the sole use of our client according to their specific requirements and instructions. Agonis Group takes no responsibility for any third party who uses or relies upon the information in the report without the written authority of Agonis Group or our client.

# Table of Contents

Table of Contents	2

Definitions, Abbreviations and Anacronyms	3

1.0	Executive Summary	4

2.0	Scope of the Review	9

3.0	Methodology for the Review	11

4.0	Key Criteria and Assumptions	12

5.0	Line Section Review	142

5.1	York (excl) - Quarading (74km) ………………………………………………………………………………………….12

5.2	Maya - Perenjori (excl) (56km) ………………………………………………………………………………………….17

5.3	Trayning - West Merredin (excl) (73km) ……………………………………………………………………………20

5.4	Narrogin (excl) - Yilliminning (incl) (23km) …………………………………………………………………………24

5.5	Yilliminning (excl) - Corrigin (incl) (85km) ………………………………………………………………………….27

5.6	Corrigin (excl) - Bruce Rock (excl) (60km) ………………………………………………………………………….33

5.7	Bruce Rock (incl) - West Merredin (excl) (48km) ……………………………………………………………….36

5.8	Yilliminning (excl) - Kulin (95km) ……………………………………………………………………………………….40

5.9	Kondinin - Narembeen (excl) (51km) …………………………………………………………………………………44

5.10	Narembeen (incl) - West Merredin (excl) (91km) ………………………………………………………………48

5.11	Katanning (excl) - Nyabing (61km) …………………………………………………………………………………….53

5.12	Tambellup (excl) - Gnowangerup (38km) …………………………………………………………………………..58

5.13	West Merredin Yard ………………………………………………………………  ……………………………………….63

6.0	Upgraded Track Structure	67

7.0	Construction Methodology	68

8.0	Basis of Estimates	71

9.0	Alternate Operational Strategies	73

10.0	Appendix 1 – Formation Works	75

11.0	Appendix 2 – Linear Asset Diagrams	76

12.0	Appendix 3 – CBH Siding Configurations	77

13.0	Appendix 4 – Bridge Works	78

14.0	Appendix 5 – Level Crossings	79

15.0	Appendix 6 – Culvert Works	80

16.0	Appendix 7A – West Merredin Yard NG Option - Schematic	81

17.0	Appendix 7B – West Merredin Yard SG Option – Schematic	82

18.0	Appendix 8 –Estimate Breakdown	83

19.0	Appendix 9 – GHD Bridge Report	84

20.0 Appendix 10 – PTA System Map	92

# Definitions, Abbreviations and Acronyms

| Item | Meaning |
| --- | --- |
| 58lb; 60lb; 63lb; 80lb; 82lb | Rail weights in pounds per linear yard |
| 31kg; 41kg; 47kg; 50kg; 60kg; 66kg | Rail weights in kilograms per linear metre |
| 1:8; 1:10 | Turnout crossing angles |
| CM | Cast manganese turnout crossing |
| Contra | Contra flexure turnout. Turnout in a curve whose curvature is in the opposite hand to the turnout angle. |
| EGR | Eastern Goldfields Railway Standard gauge interstate railway |
| FBW | Flashbutt weld |
| FL | Active flashing light road crossing protection |
| MGTPA | Million gross tonnes per annum |
| NG | Narrow gauge railway track (1067mm) |
| RBCM | Rail bound cast manganese turnout crossing |
| RCB | Reinforced concrete box culvert structure |
| RCP | Reinforced concrete pipe culvert structure |
| RTC | Rail top culvert |
| SG | Standard gauge railway track (1435mm) |
| Sim | Similar flexure turnout. Turnout in a curve whose curvature is in the same hand as the turnout angle. |
| Spring | Spring nose turnout crossing. Trailable points |
| SN | Spliced nose turnout crossing |
| tal | tonne axle load |

# Executive Summary

The Public Transport Authority of West Australia (PTA) commissioned Agonis Group to undertake an engineering review of the works required and the associated cost to reinstate the Tier 3 Grain Lines in the WA freight network to operational condition. The PTA Rail System Map is included in Section 21 – Appendix 11.

The review comprised 2 parts. The first part required all lines to be retained in NG configuration. The second part required the lines feeding into West Merredin to be converted to SG. Selected CBH siding facilities were included for assessment and rehabilitation to accommodate likely train configurations.

The minimum operating standard required on each line was to permit 19tal trains to run at a maximum loaded speed of 80kph for a task of 1 MGTPA in all weather over a life of 30 years.

The Maya to Perenjori section was to be limited to 16tal as it feeds into a 16tal operational railway.

The methodology undertaken to satisfy the requirements of the review is detailed in Section 3.

The cost findings of the engineering review for Part 1 are summarised in Table 1.1 below.

1.1 	Budget Estimate Costing

Table 1.1

| Line Section # | Sub Section | Cost AUD$M |
| --- | --- | --- |
| 33 | York (excl) to Quairading (incl) | $109.53 |
|  | Loops/CBH Siding: Quairading | $1.38 |
|  | Sub Total | $110.91 |
| 34 | Maya (incl) to Perenjori (excl) | $74.16 |
|  | Loops/CBH Siding: Maya | $3.43 |
|  | Sub Total | $77.59 |
| 35 | Trayning (incl) to West Merredin (excl) | $100.64 |
|  | Loops/CBH Sidings: Trayning; Nungarin | $4.75 |
|  | Sub Total | $105.39 |
| 59 | Narrogin (excl) to Yilliminning (incl) | $34.54 |
|  | Sub Total | $34.54 |
| 59 | Yilliminning (excl) to Corrigin (incl) | $118.06 |
|  | Loops/CBH Sidings: Wickepin; Corrigin | $8.55 |
|  | Sub Total | $126.61 |
| 59 | Corrigin (excl) to Bruce Rock (excl) | $77.40 |
|  | Loops/CBH Sidings: Ainsworth | $2.32 |
|  | Sub Total | $79.72 |
| 59 | Bruce Rock (incl) to West Merredin (excl) | $70.90 |
|  | Loops/CBH Siding: Bruce Rock | $5.54 |
|  | Sub Total | $76.44 |
| 60 | Yilliminning (excl) to Kulin (incl) | $123.46 |
|  | Loops/CBH Sidings: Nomans Lake; Dudinin; Kulin | $6.41 |
|  | Sub Total | $129.87 |
| 60 | Kulin (excl) to Kondinin (excl) | Non operational |
| 60 | Kondinin (incl) to Narembeen (excl) | $67.49 |
|  | Loops/CBH Sidings: Kondinin; Sth Kumminin | $3.61 |
|  | Sub Total | $71.10 |
| 60 | Narembeen (incl) to West Merredin (excl) | $132.89 |
|  | Loops/CBH Sidings: Narembeen; Muntadgin | $6.68 |
|  | Sub Total | $139.57 |
| 63 | Katanning (excl) to Nyabing (incl) | $83.95 |
|  | Loops/CBH Siding: Nyabing | $3.81 |
|  | Sub Total | $87.76 |
| 64 | Tambellup (excl) to Gnowangerup (incl | $53.44 |
|  | CBH Siding: Gnowangerup | $2.49 |
|  | Sub Total | $55.93 |
| 35/59/60 | West Merredin Yard | $4.44 |
| TOTAL |  | $1,099.87 |

The second part of the engineering review required an assessment of the cost to convert the lines feeding into West Merredin to SG under the same operating parameters. This allows grain trains from these Tier 3 lines to be consolidated into longer consists at West Merredin Yard and then proceed directly to Kwinana on SG.

The cost findings for Part 2 are summarised in Table 1.2 below.

Table 1.2

| Line Section # | Sub Section | Cost AUD$M |
| --- | --- | --- |
| 35 | Trayning (incl) to West Merredin (excl) | $111.24 |
|  | Loops/CBH Sidings: Trayning; Nungarin | $5.56 |
|  | Sub Total | $116.80 |
| 59 | Bruce Rock (incl) to West Merredin (excl) | $79.97 |
|  | Loops/CBH Sidings: Bruce Rock | $6.90 |
|  | Sub Total | $86.87 |
| 60 | Kondinin (incl) to Narembeen (excl) | $75.74 |
|  | Loops/CBH Sidings: Kondinin; Sth Kumminin | $4.41 |
|  | Sub Total | $80.15 |
| 60 | Narembeen (incl) to West Merredin (excl) | $149.61 |
|  | Loops/CBH Sidings: Narembeen; Muntadgin | $8.32 |
|  | Sub Total | $157.93 |
| 35/59/60 | West Merredin Yard | $5.70 |
| TOTAL |  | $447.45 |

1.2 	Alternate Operating Strategies

There are other strategies which could be employed to resume train operations on the Tier 3 lines. These will require a reduction in the operating regime specified in the engineering review scope in Section 2.

They are identified for consideration and the scopes of work are covered in Section 9 of the report. Evaluation of these alternate strategies are not part of this engineering review, however, indicative estimates for Strategy 9.1 (Retain as existing) are included in Table 1.3 below for comparison.

Table 1.3

| Line Section # | Sub Section | Cost AUD$M |
| --- | --- | --- |
| 33 | York (excl) to Quairading (incl) | $59.41 |
|  | Loops/CBH Siding: Quairading | $0.62 |
|  | Sub Total | $60.03 |
| 34 | Maya (incl) to Perenjori (excl) | $30.83 |
|  | Loops/CBH Siding: Maya | $0.89 |
|  | Sub Total | $31.72 |
| 35 | Trayning (incl) to West Merredin (excl) | $42.87 |
|  | Loops/CBH Sidings: Trayning; Nungarin | $1.54 |
|  | Sub Total | $44.41 |
| 59 | Narrogin (excl) to Yilliminning (incl) | $17.3 |
|  | Sub Total | $17.3 |
| 59 | Yilliminning (excl) to Corrigin (incl) | $57.19 |
|  | Loops/CBH Sidings: Wickepin; Corrigin | $3.09 |
|  | Sub Total | $60.29 |
| 59 | Corrigin (excl) to Bruce Rock (excl) | $36.20 |
|  | Loops/CBH Sidings: Ainsworth | $0.64 |
|  | Sub Total | $36.84 |
| 59 | Bruce Rock (incl) to West Merredin (excl) | $32.55 |
|  | Loops/CBH Siding: Bruce Rock | $2.31 |
|  | Sub Total | $34.86 |
| 60 | Yilliminning (excl) to Kulin (incl) | $55.14 |
|  | Loops/CBH Sidings: Nomans Lake; Dudinin; Kulin | $3.39 |
|  | Sub Total | $58.53 |
| 60 | Kulin (excl) to Kondinin (excl) | Non operational |
| 60 | Kondinin (incl) to Narembeen (excl) | $30.29 |
|  | Loops/CBH Sidings: Kondinin; Sth Kumminin | $1.43 |
|  | Sub Total | $31.72 |
| 60 | Narembeen (incl) to West Merredin (excl) | $58.73 |
|  | Loops/CBH Sidings: Narembeen; Muntadgin | $2.33 |
|  | Sub Total | $61.06 |
| 63 | Katanning (excl) to Nyabing (incl) | $41.29 |
|  | Loops/CBH Siding: Nyabing | $0.92 |
|  | Sub Total | $42.22 |
| 64 | Tambellup (excl) to Gnowangerup (incl | $23.65 |
|  | CBH Siding: Gnowangerup | $0.74 |
|  | Sub Total | $24.38 |
| 35/59/60 | West Merredin Yard | $4.44 |
| TOTAL |  | $507.78 |

# Scope of the Review

The detailed scope of the engineering review requested by the PTA is described below.

The Tier 3 rail network currently comprises:

| Line Section | Axle load | Sleepers | Rail | Ballast |
| --- | --- | --- | --- | --- |
| Trayning to West Merredin | 16 | 1:4 Steel | 60lb 63lb 41kg | Gravel |
| West Merredin to Narrogin via Corrigin | 16 | 1:4 Steel (Bruce Rock Ardath Timber) | 60lb 63lb 80lb | Metal (Bruce Rock Ardath Gravel) |
| West Merredin to Narrogin via Kondinin | 16 | 1:4 Steel (Yilliminning to Wickepin Timber) | 60lb 63lb 30, 31 and 41kg | Metal (Yilliminning to Wickepin and Nomans Lake Gravel) |
| Tambellup to Gnowangerup | 16 | 1:4 Steel | 60lb | Gravel |
| Katanning to Nyabing | 16 | Timber | 60lb | Katanning to Badgebup Metal, Badgebup to Nyabing Gravel |
| York to Quairading | 16 | 1:4 Steel | 58, 60 and 63lb | Gravel |
| Perenjori - Maya | 16 | Timber | 63lb | Gravel |

The PTA Rail System Map is included in Section 21 – Appendix 11.

The purpose of the review is to establish the condition of the Tier 3 network and provide detailed costings for either the rehabilitation or rebuild, or combination of both, of the Tier 3 network, as determined by the findings of the review.

The review is to examine and report on the condition of all rail infrastructure assets including but not limited to:

- Level crossings.

- Bridges and culverts.

- Rail, sleepers and ballast.

- Road vehicle access to the lines.

- Turnouts; and

- Communications (Lineside phones).

The minimum operating standard following rehabilitation or rebuild is to  accommodate NG 19 tonne axle load  at a maximum speed of 80kph (reduced as necessary for curvature and other existing constraints) for a line haul of 1MGTPA in all weather over a life of 30 years. Perenjori – Maya is to remain at 16 tonne axle load (as Perenjori – Morawa at 16tal is a constraint).

Changes to the track and centreline structures will be necessary to provide for 19 tonne axle loads and the review should consider and advise replacement options (such as metal ballast, replacement rail weights, low profile concrete sleepers and centreline structures).

The review is to include assessment of CBH siding rail infrastructure at Primary and Secondary locations as listed below. The siding review should report on rehabilitating existing rail infrastructure with consideration given to upgrading CBH Primary locations to accommodate current train configurations (train length). It is not anticipated that configuration layout changes to any sidings or yards will be considered other than for any obvious operational improvements.

| Primary CBH Locations | Narembeen; Kondinin; Kulin; Dudinin; Nomans Lake; Quairading; Trayning; Bruce Rock; Corrigin |
| --- | --- |
| Secondary CBH Locations | Nungarin; Muntadgin; South Kumminin; Ainsworth; Wickepin; Nyabing; Gnowangerup |

Re-opening feeder lines into West Merredin will also require assessment of rail infrastructure at the Merredin CBH transfer facility.

Ongoing maintenance costs shall be considered only if the recommended rebuild/rehabilitation may result in a significant increase over and above normal.

Once the NG baseline has been established, the review must consider and report on the option of converting lines which feed into West Merredin to SG.

# Methodology for the Review

A full on-track inspection of the entire Tier 3 network was not possible. In many locations the railway has been fenced off by farmers and trees and shrubs have grown in the track formation. Track has also been washed away in many places.

Consequently, site inspections were undertaken by road vehicle and targeted at strategic assets such as bridges, level crossings, sidings, CBH facilities and selected sections of track and formation. Track condition was sampled at random locations and culverts were viewed where road vehicle access permitted. Recent rain in the review area made some sections inaccessible by road vehicle.

Detailed asset lists of bridges and culverts dating from 1999 were provided by the PTA. Asset register information was requested by PTA from Arc Infrastructure as the incumbent asset lessee. This information was subsequently provided part way through the program of site inspections. Asset register information was then able to be validated during site inspections, thus providing a level of confidence in the assumptions made on the extent of works required for rehabilitation. These asset registers were found to be out of date in some areas and did not accurately reflect the current status (particularly regarding culverts).

Inspection notes and photographs were recorded at each bridge (bar 2 structures which were inaccessible), sealed public level crossings, turnouts at all sidings, CBH sidings, typical samples of culverts and sections of track, formation banks and cuttings. These were used as the reference for developing the scope of work required to be undertaken so that costs could be reasonably estimated.

Schematic diagrams supplemented by site inspection were used to determine works required in West Merredin to accommodate the reconnection of NG and the conversion to SG under part 2 of the brief.

Schematic diagrams of each of the primary and secondary CBH sidings were developed from the inspection notes and photographs to determine any work necessary to accommodate the proposed train configurations.

An independent structural assessment of a sample of bridges with steel beams or ballasted steel decks was requested from GHD, to provide guidance as to their likely suitability to be retained under 19tal. This was undertaken without detailed drawings or knowledge of the condition of the foundations, and only based on photographs and the detail contained in the asset registers.

The load rating of reinforced concrete pipes (RCP) is, in most cases, not specified in the asset registers and could not be readily determined from site inspection. In these cases, where it could be identified that an RCP had formation cover more than 750mm then it was assessed to be suitable to retain under 19tal. Where the load rating was identified as M250 in the registers, the RCP’s were generally retained, subject to any adverse site inspection findings.

The engineering review was undertaken without reference to Arc Infrastructure or CBH.

# Key Criteria and Assumptions

In a high-level review of this nature, there are necessarily a number of key criteria and assumptions which underpin the output of the report. These are documented below.

- Enquiries have determined that the most likely train consist is a single CBH Class locomotive hauling 15 paired CBH wagons at 32 metre length per pair over the couplers. This gives a total consist length of 498.5 metres. Standing room of 500 metres has been allowed in assessing the works required for run-around and loading facilities. In most cases, at primary and secondary CBH loading locations, this means that the train consist will be fouling the mainline at one end or the other during loading operations. It is considered that this is a manageable operating scenario for the annual haulage task.

  - Efficient train operations in the current era provide for grain wagons to be loaded under power. It has been assumed that all CBH train loading will be undertaken under power. This requires rapid loading and fast turnaround often with a train crew of 1 driver. The configuration and operation of Tier 3 lines will require a train crew of 2 to facilitate train run-around and setting back for loading.

  - In some cases, the loading of a 500m train consist will block level crossings at one end or the other during train loading operations. The duration of the obstruction will be dependent on the CBH loading rate and the position of the load out chutes relative to the train consist. It has been assumed that this arrangement will be acceptable to the road users and no attempt has been made to verify this or propose any solution.

4.4	No longitudinal gradient profiles for the Tier 3 grain lines was available. The assumption is that grades will be suitable for the operation of the train consist of 30 wagons hauled by a CBH Class locomotive, albeit at lesser speed on steeper grades.

4.5	No attempt has been made to assess the cost of upgrading or establishing grain handling and fast train loading facilities at proposed new rail sidings, or primary and secondary CBH terminals. 
Existing grain loading configurations are set up for a system of daily loading by drifting wagons under a low speed load out chute for pick up at the end of the day. This is not current practice and is inefficient. Existing facilities are unlikely to be suitable for recommissioning without major upgrading.

4.6	In many locations CBH has established major purpose-built facilities for storage and loading of grain onto road trucks. These facilities are not directly adjacent to the existing railway (although in the general area) and specific sidings will need to be constructed to access these sites. It is assumed that rapid train loading facilities will be established by others. No attempt has been made to assess the cost of establishing these facilities.

  - There has been no opportunity to inspect and record the entire length of each line. Selected sampling only has been undertaken of formation, track, culverts and road crossings. Each turnout, bridge (bar 2) and sealed public level crossing has been inspected and documented.

  - Culvert asset register information provided was found to be incomplete and/or out of date in some sections. Assumptions have been made on the load capacity, waterway capacity, depth of cover and general condition of most of the culverts. These assumptions at each location are documented in Appendix 6. No hydrological assessment has been undertaken and areas subject to inundation and washaway remain.

  - Assumptions are made on the extent of embankment widening and soft formation renewal necessary to retain a full metal ballast profile and support all weather 19tal at 80kph. This is particularly significant for the SG option.

  - The load capacity of a sample of transom and ballasted steel deck bridges with steel and concrete substructures has been assessed by GHD. Results have been extrapolated for other structures and conclusions made on their retention or replacement. Proposed works for each bridge structure is documented in Appendix 4.

  - For the SG option for lines feeding into West Merredin, it is assumed that trains will continue directly on SG to Kwinana. It is assumed that loaded wagons may be combined and consolidated into longer trains between West Merredin and Kwinana and track has been allowed to provide for this. Track layout at West Merredin is schematic and the viability of the geometry is yet to be validated.

  - There has been no interaction with CBH, Arc Infrastructure or train operators. Efficient transport of grain for export must be a coordinated logistics chain from paddock to ship.

  - No attempt has been made to reassess the level of protection at public and private level crossings. The Australian Level Crossing Assessment Model (ALCAM) is an assessment tool used to identify key potential risks at level crossings and to assist in the prioritisation of crossings for upgrades. The risk model is used to support a decision-making process for both road and pedestrian level crossings and to help determine the most appropriate treatments to improve safety. This will be required prior to recommencement of train operations.

  - No provision is made for retaining and upgrading crossing loops at intermediate locations. It is considered that the annual haulage task can be adequately managed using the proposed CBH primary and secondary sidings without the need to cross trains mid-section.
Any mainline turnouts other than those needed to service the CBH sidings can be removed and replaced with plain track.

  - The review has been undertaken in compliance with the Brookfield Rail NG Code of Practice Reference NG CoP and Australian Standards relevant to the works and material supply.

# Line Section Review

This section should be read with reference to Appendix 1 - Formation Works, Appendix 2 - Linear Asset Diagrams, Appendix 3 - CBH Siding Configurations, Appendix 4 - Bridge Replacements, Appendix 5 - Level Crossings and Appendix 6 - Culvert Works as appropriate.

5.1	York (excl) to Quairading (incl) (74km)

5.1.1	Background

The York - Quairading section became non-operational in September 2013 It last operated at 16tal at 30kph loaded under a Train Order system. Gross tonnage varied up to 0.25MGTPA.

The last resleepering cycle was undertaken in 98/99 and established a 1:4 steel/timber configuration. The section is now generally in poor condition.

5.1.2	Track and Formation

Refer Appendix 1 and Appendix 2.

Rail is primarily 60lb jointed track in 12m lengths. Some level crossings are 80lb rail with sections of 80lb/41kg and 47kg rail in the first 7km out of York.

Sleepers are 1:4 steel/unplated timber. Timber sleepers are in fair/good condition probably because the section being non-operational for an extended period after the last resleepering cycle.

The section is in gravel ballast of generally good quality. Some level crossings are metal ballasted

Between York and Mawson the terrain is undulating. Railway banks and cuttings vary up to 2-3 metres in height/depth. Generally, cuttings are of sufficient width and will only require drain cleaning following track upgrading.

7km of banks 1.5 – 2.5m in height will require widening by up to 0.5m each side to retain the upgraded track ballast profile.

Banks from Mawson to Quairading are generally lower in the 0.5 – 1.5m range. There are some short sections of bank scour and isolated washaways.

Approx. 5km of these banks will require widening by 0.5m each side for track upgrading.

35km of existing track formation will require nothing more than compaction of the shoulders following removal of the gravel ballast.

P0882 – 60.90km

5.1.3	Turnouts

Existing mainline turnouts at Greenhills and Mawson are 82lb 1:10 configuration on 1:2 steel bearers in metal ballast and are in excellent condition. The turnouts at Mawson are SN, and the turnouts at Greenhills are RBCM crossings.

As the sidings at these 2 locations are redundant, the 4 turnouts will be removed and replaced with plain track. The turnouts will be available for reuse at other locations in the upgraded Tier 3 lines.

Quairading is the end of the line section. The 2 turnouts at either end of the loop are both 63lb 1:10 SN configuration. At the York end the turnout is on 1:2 steel bearers in metal ballast and is in good condition. As it will only be used at low speed during run-around operations with empty wagons, a case could be made for its retention. However, the main and loop must be upgraded to 41kg rail so this turnout will be replaced. At the Quairading end, the turnout is on 1:4 steel bearers in gravel ballast. It is in fair condition but, given that it will be relocated to provide 500m standing room, it will be replaced.

5.1.4	Bridges and Culverts

There are 10 bridge structures in this line section. 1-33 span, 1-11 span, 1-7 span and the remainder 1, 2 or 3 spans. Proposals for treatment are underpinned by the GHD structural assessment of a sample of steel bridge beams.

2.330km Avon River

P0915 and P0917

This is the most significant bridge structure in the Tier 3 Grain Network. There are 33 spans of lengths between 3.75m to 5.94m in length at nominal waterway depths of 4.70m to 6.50m. The spans over the main river channel (6.50m waterway depth) are steel ballasted decks on a steel and concrete substructure and are of relatively recent construction. It is assumed that these 6 steel spans may be retained under the upgraded operating regime.

The remaining 27 spans on the floodplain either side (average 4.70m waterway depth) which are primarily timber ballasted decks on timber piles in poor condition will need to be replaced. 3 of these spans have been upgraded with steel at some time, however, their condition cannot be certain for 19tal and replacement is recommended.

22.412km Bailey Brook

This is an 11- span transom deck bridge with steel spans (nominally 4.50m) on concrete piers. The piers are skewed approximately 30 degrees from the track to align with the stream flow. It is in good condition overall but does not have walkways for safety refuge.
The beams have been assessed as inadequate under the upgraded operating regime and, therefore, it is proposed to upgrade the beams, renew the transoms and add a walkway.
P0906

29.450km Kauring

This is a 7-span timber ballasted deck bridge on timber beams with steel ballast beams and steel sheeted abutments on a timber substructure with concrete pile caps. Nominal spans are 4.50m with a waterway depth of approximately 2.7m in the main channel.
This structure will be replaced.

P0901

Based on the structural assessment of bridge beams, the beams in the following bridges are considered inadequate for 19tal under the upgraded operating regime.

3.006km 	1-span transom deck on steel beams and concrete abutments. Replace with 2-2100 x 1800 RCB.

15.091km 	3-4.50m span ballasted steel spans on steel corbels with concrete piers and abutments. Replace with 5-2700 x 1200 RCB.

15.950km 	2-4.50m span ballasted steel spans on steel corbels with concrete piers and abutments. Replace with 4-2100 x 1500 RCB.

20.074km 	3-4.50m span ballasted steel spans on steel corbels with concrete piers and abutments. Replace with 5-2400x1800 RCB.

34.890km 	3-4.50m span ballasted steel spans on steel corbels with concrete piers and abutments. Replace with 5-2700 x 1200 RCB.

36.920km 	2-4.50m span ballasted steel spans on steel corbels with concrete piers and abutments. Replace with 5-1800 x 900 RCB.

51.980km 	3-4.50m span ballasted steel spans on steel corbels with concrete piers and abutments. Replace with 4-2400 x 1200 RCB.

There are 695 culverts of different types listed in the asset register for this line section. Some were found to have been removed or already replaced by upgraded structures.

Approximately 650 of the culverts listed in the Arc Infrastructure Asset Register are rated at M250 loading. These are therefore assumed to be structurally adequate. They may require either pipe length extension to accommodate the widened formation shoulders, or have ballast retaining beams installed to retain the widened formation shoulders.

The remaining 45 culverts are structures which are deemed to be inadequate for the upgraded operating regime and are mostly recommended for replacement. They may require pipe length extension to accommodate the widened formation shoulders, or have ballast retaining beams installed to retain the widened formation shoulders.

The proposed treatment of each culvert is specified in Appendix 6.

5.1.5	Level Crossings

Level crossings in this line section are summarised in the Table.

| TYPE | PROTECTION | NUMBER |
| --- | --- | --- |
| Public sealed | Active | 10 |
| Public sealed | Passive | 3 |
| Public unsealed | Passive | 12 |
| Private/occupation | Passive | 21 |

2 of the public sealed crossings are constructed with 60lb rail. The others are all 80lb, 82lb or 41kg rail with a variety of 1:4 steel sleepers and pandrol plated timber or plain timber.

The condition of the sealed road surfaces are variable with a few retaining the older timbers which have been sealed over.

All road crossings will be upgraded to 41kg rail on concrete sleepers in metal ballast. Drainage improvements will be undertaken, and geotextile used to ensure to ongoing effectiveness of the ballast and drainage.

All active protection flashlights will need to be recommissioned and allowance has been made in the estimate.

Details of the level crossings are contained in Appendix 5. An ALCAM assessment will likely be required prior to any train operations.

5.1.6	Access to the Track

Inspections were undertaken by road vehicle. For most of the line section length it was possible to drive along the fire breaks and railway access roads. It was fortunate that there had not been recent rainfall, as this would have made the task less comfortable. It is not all-weather access.

Between the 23-29km the farmer has cultivated the railway reserve right up to the toe of the embankment and removed the railway KM markers and any associated railway signage. This will need to be reclaimed and the access track regraded.

Closer to York where the terrain becomes more undulating, access along the railway is not as easy, however, there are adjacent gravel public roads which provide access to the railway at convenient points.

Access will be created during the process of track upgrading; however, this will not necessarily provide all weather access for road vehicles immediately adjacent to the track.

At the time of the inspection, access would be classified as fair.

5.1.7	Communications

Telstra 3G
The line section has reasonable coverage. York to Greenhills has some dark sections due to topography. Greenhills to Quairading is mostly covered but again there are some shorter dark sections.

Train control must use the train radio network and landlines from Train Order cabins or utilise satellite telephones.

5.1.8	CBH Sidings

Quairading

At Quairading the loading of grain wagons occurs on the mainline. 

The existing loop at Quairading must be extended by approximately 30m to allow run-around facilities for a train consist of 500m. This is achievable and will allow operations without obstructing the McLennan Street level crossing for any extended period.

The CBH rail grain loading chute is 300m west of the flashlight protected level crossing at Ashton Street. If the grain train configuration is retained at 500m, then this level crossing will be blocked for an extended period during train loading. There is alternative access for the community across the railway at McLennan Street to the east of the extended loop. This will undoubtedly cause inconvenience as Ashton Street is the primary crossing.

5.2	Maya (incl) to Perenjori (excl) (56km)

5.2.1	Background

The Maya - Perenjori section became non-operational in June 2014. It last operated at 16tal at 30kph loaded under a Train Order system. Gross tonnage varied up to 0.5MGTPA.

The last resleepering cycle was undertaken in 99/00 and established a 1:4 steel timber configuration. The section is now generally in fair/good condition.

This line section is to remain at 16tal under the proposed operating regime.

5.2.2	Track and Formation

Refer Appendix 1 and Appendix 2.

Rail is 63lb continuously welded.

Sleepers are 1:4 steel/unplated timber. Some curves are fitted with standard sleeper plates. Timber sleepers are in fair/poor condition with at least 75% requiring renewal.

The section is in gravel ballast of generally good quality over the entire length.

The vertical alignment generally follows the ground profile with shallow cuttings and low banks (0.5 – 1.5m).  Cutting widths are considered adequate over the entire line section. Cuttings will require clean out following track upgrading.

Approximately 5km of banks up to 1.5m will require widening by up to 0.5m each side, and the shoulders of the remaining banks will require compaction following removal of the gravel ballast. 
P1003 – 262km.

5.2.3	Turnouts

Mainline turnouts at Maya (2), Latham (2) and Bunjil (2) are 82lb rail on 1:2 steel/timber bearers in metal ballast. The south end at Latham is a contraflexure turnout. All are in excellent condition and suitable for reuse.

Maya CBH will be retained in its current configuration so the existing turnouts will be retained.

As Latham and Bunjil are intermediate sidings, the mainline turnouts will be removed and replaced with plain track. These 4 turnouts are then available for reuse for upgrading the remaining Tier 3 lines. The likelihood of finding a location to reuse the contra flexure turnout from Latham is remote.

5.2.4	Bridges and Culverts

There are no bridge structures in this line section.

The 834 culverts in the line section are primarily RCP’s which have been extended to accommodate a 6.0m formation width. None of the culverts are load rated, however, they have previously been performing under the proposed 16tal operating regime and are deemed adequate.

Only 1 requires extension. 2 require new headwalls.

The 2 rail top culverts (RTC) only require new transoms.

Apart from these minor items, all culverts are considered adequate for the new operating regime.

The proposed treatment of each culvert is specified in Appendix 6.

5.2.5	Level Crossings

Level crossings in this line section are summarised in the Table.

| TYPE | PROTECTION | NUMBER |
| --- | --- | --- |
| Public sealed | Active | Nil |
| Public sealed | Passive | 4 |
| Public unsealed | Passive | 11 |
| Private/occupation | Passive | 15 |

3 the public sealed crossings are constructed with 63lb rail on 1:4 steel/timber in gravel ballast. The crossing at Bunjil North East Rd is in 82lb rail.

Sealed road surface conditions are variable. One has not been resealed following track maintenance.

All road crossings will be upgraded to 41kg rail on concrete sleepers in metal ballast. Drainage improvements will be undertaken, and geotextile used to ensure to ongoing effectiveness of the ballast and drainage.

Details of the level crossings are contained in Appendix 5. An ALCAM assessment will likely be required prior to any train operations.

5.2.6	Access to the Track

The main road runs parallel (20 – 100m) with the railway for the majority of the line section and there are many road access points to the railway.

Most of the line section was inspected from the firebreaks or by driving along the shoulder of the formation. This area is generally drier as it is further north than other sections of the Tier 3 lines, however, it does not ensure all weather road vehicle access.

There are 2 sections of approximately 200 – 300m which have been fenced to the toe of embankment on one or both sides to protect rare flora.

Access will be created during the process of track upgrading, however, this will not necessarily provide all weather access for road vehicles immediately adjacent to the track. Clearing of firebreaks will improve access significantly.

At the time of the inspection, access would be classified as satisfactory

5.2.7	Communications

Telstra 3G
The line section has full coverage, due primarily to mining activities in the region.

Train control must use the train radio network and landlines from Train Order cabins or utilise satellite telephones.

5.2.8	CBH Sidings

Maya

All grain from Maya will be hauled north to Geraldton. Maya is, therefore, the end of the line.

The CBH loading chute is over the loop line. The train consist will pull into the loop, run-around with the loco and then push back onto the mainline at the south end to commence loading.

Mainline turnouts at each end are 82lb 1:10 SN 1:2 steel/timber in metal ballast and will be retained. The only track works required is to upgrade the loop and mainline to the new operating standard.

5.3	Trayning (incl) to West Merredin (incl) (73km)

5.3.1	Background

The Trayning – West Merredin section became non-operational in September 2013 It last operated at 16tal at 30km/h loaded under a Train Order system. Gross tonnage varied up to 0.3MGTPA.

The last resleepering cycle was undertaken in 1988/1989. The section is now generally in poor condition.

5.3.2	Track and Formation

Refer Appendix 1 and Appendix 2.

Between Trayning (109km) and Nungarin (142km) the track is 60lb jointed rail.
Sleepers are nominally 1:4 steel/unplated timber sleepers which have been adjusted for rail joints. Joints have 2 timber sleepers each side. Timber sleepers are in fair-poor condition and will require renewal.
Ballast is gravel of generally good quality.
P0816 – 110.80km.

From Nungarin to West Merredin (182km) the track is 63lb jointed rail.
Sleepers are nominally 1:4 steel/unplated timber sleepers which have been adjusted for rail joints. Joints have 2 timber sleepers each side. Some curves are fitted with standard sleeper plates and 1:2 steel/timber sleepers. Timber sleepers are in fair-poor condition with at least 75% requiring renewal.
Ballast is gravel of generally good quality. The last 2km into West Merredin is metal ballast.

The vertical alignment generally follows the ground profile with shallow cuttings and low banks (0.5 – 1.5m).  
Cutting widths are considered adequate over the entire line section. Approximately 17km of cuttings will require clean out following track upgrading.

62km of banks require no work other than compaction of shoulders after the grading out of gravel ballast.

Approximately 4km of banks up to 1.5m will require widening by up to 0.5m each side, and the shoulders of the remaining banks will require compaction following removal of the gravel ballast.

5.3.3	Turnouts

At the existing Trayning CBH siding, the mainline turnouts are 60lb 1:10 on timber bearers in gravel ballast. The Trayning end is a spring nose crossing and the West Merredin end is a SN crossing. They are in poor condition.

As a new siding into the CBH road facility is proposed approximately 400m to the West Merredin side of Trayning, these 2 turnouts will substantially redundant. If the siding is retained for crippled wagon storage, then the turnouts should be replaced. Recovered 82lb turnouts from Latham/Bunjil could be utilised.

At Nungarin, the 2 mainline turnouts are 82lb 1:10 SN on steel bearers in metal ballast. They are in excellent condition and will be retained. The turnout at the West Merredin end will be relocated by 80m towards West Merredin to provide 500m standing room.

The turnout to be retained in the CBH siding for crippled wagon storage is 63lb 1:10 SN on timber bearers in gravel ballast and is in poor condition. It should be replaced with one of the turnouts from Maya-Perenjori.

The intermediate CBH sidings at Kununoppin and Nukarni are redundant, and the mainline turnouts will be removed and replaced with plain track. Kununoppin mainline turnouts (4) are 63lb 1:10 SN on timber bearers with random steel in gravel ballast. Nukarni mainline turnouts are 63lb 1:10 SN on 1:2 steel/timber bearers in gravel ballast.

5.3.4	Bridges and Culverts

There are no bridge structures in this line section.

There are approximately 127 culverts listed for this line section. 100 of these are rated for M250 loading. These are therefore assumed to be structurally adequate. They may require either pipe length extension to accommodate the widened formation shoulders, or have ballast retaining beams installed to retain the widened formation shoulders.

The remaining 27 culverts are structures which are deemed to be inadequate for the upgraded operating regime and are mostly recommended for replacement.

They may require pipe length extension to accommodate the widened formation shoulders, or have ballast retaining beams installed to retain the widened formation shoulders.

P0842 – 155.20km.

The proposed treatment of each culvert is specified in Appendix 6.

5.3.5	Level Crossings

Level crossings in this line section are summarised in the Table.

| TYPE | PROTECTION | NUMBER |
| --- | --- | --- |
| Public sealed | Active | 2 |
| Public sealed | Passive | 11 |
| Public unsealed | Passive | 10 |
| Private/occupation | Passive | 10 |

1 of the active public sealed crossings is 82lb and the other is 60kg. All the remaining crossings are all 60lb on timber sleepers. Only a few are pandrol plated.

The condition of the sealed road surfaces is variable but mostly good to fair condition.

All road crossings (bar 1) will be upgraded to 41kg rail on concrete sleepers in metal ballast. Drainage improvements will be undertaken, and geotextile used to ensure to ongoing effectiveness of the ballast and drainage. The 60kg crossing at Gamenya Rd will be retained.

P0828 – 124.30km.

All active protection flashlights will need to be recommissioned and allowance has been made in the estimate.

Details of the level crossings are contained in Appendix 5. An ALCAM assessment will likely be required prior to any train operations.

5.3.6	Access to the Track

The main road runs parallel (20 – 100m) with the railway for most of the line section and there is a railway access road/firebreak on the opposite side of the railway. Unsealed local roads are also available over many sections, running parallel with the railway on the north-east side.

Most of the line section was inspected from the access road/firebreaks or local unsealed roads. This area is generally drier as it is further north than other sections of the Tier 3 lines and there had not been any recent rain. The access road/firebreak would be impassable in many areas in wet weather.

There are level crossing and occupation crossing providing access points to the railway.

Access will be created during the process of track upgrading, however, this will not necessarily provide all weather access for road vehicles immediately adjacent to the track. Clearing of firebreaks will improve accessibility.

At the time of the inspection access would be classified as good.

5.3.7	Communications

Telstra 3G
This section has full coverage from the Telstra 3G network.

Train control must use the train radio network and landlines from Train Order cabins or utilise satellite telephones.

5.3.8	CBH sidings

Refer Appendix 3

Trayning

Grain from Trayning is hauled to West Merredin. Trayning is the end of the line.

The old CBH rail loading facility in Trayning does not appear to be in use with a road truck operation. 

A new road transfer facility has been established by CBH approximately 500m on the West Merredin side of Trayning. It is proposed that a new rail loading siding be constructed into this facility. This will require 2 new mainline turnouts and approximately 700 – 800m of new siding formation, drainage and track. It will also require CBH to establish a rail loading facility at this site.
 
P0815 – 110.80km.

It is recommended that the existing siding in Trayning be retained as potential storage for crippled wagons. The 2 existing mainline turnouts should be replaced with recovered 63lb turnouts from elsewhere in the Tier 3 network, and minor steel resleepering undertaken (1:2 steel) to retain gauge. 

Nungarin

The existing rail facility at Nungarin is a complex layout which can be significantly simplified.

It is proposed that the existing loop, scissors crossover and loading dead ends be made redundant and be replaced with a single upgraded loading loop under the 2 CBH load out chutes. A single dead end can be retained for crippled wagons if required.

Standing room on the existing loop is only 420m, so the turnout at the West Merredin end will need to be relocated 80m towards West Merredin. The train consist will project onto the mainline at either end at the commencement and completion of grain loading. This will alternately block the CBH entry roads at the Trayning end (commencement) and West Merredin end (completion) for periods of time. The duration of any obstruction will depend on the CBH load out rate.

The existing mainline turnouts are both 82lb 1:10 SN on steel bearers in metal ballast. They can be retained (Trayning end) and relocated (West Merredin end).

5.4	Narrogin (excl) to Yilliminning (incl) (23km)

5.4.1	Background

The Narrogin – Yilliminning section became non-operational on 30 June 2014. It last operated at 16tal at 60kph empty and 50kph loaded under a Train Order system. Gross tonnage varied up to 0.6MGTPA.

The last resleepering cycle was undertaken in 1999, establishing a 1:4 steel/timber pattern using predominantly second hand timber sleepers. The section is now generally in fair/poor condition.

5.4.2	Track and Formation

Refer Appendix 1 and Appendix 2.

Rail is primarily 63lb CWR with some sections of 31kg, 41kg and 50kg in level crossings between 0.0km and 1.7km. 
Sleepers are 1:4 steel/unplated timber.
The section is in metal ballast.

Cutting widths are considered adequate over the entire line section. 
Approximately 5km of cuttings will require clean out following track upgrading.

Approximately 2km of banks up to 1.5m will require widening by up to 0.5m each side.
The remaining 16km of banks require no work other than compaction of shoulders after the grading out of gravel ballast.

5.4.3	Turnouts

The NG crossover at Narrogin between the GSR and the Yilliminning line is 41kg 1:10 RBCM on fully pandrolised timber bearers and is in good condition. It does not require upgrading and can be retained.

At Yilliminning Junction, the junction turnout is 41kg 1:10 RBCM on fully pandrolised 1:2 steel/timber bearers. It is in good condition and will be retained.

The crossover at Yilliminning Junction between the Kulin and Corrigin lines is 63lb 1:10 SN on timber bearers. This crossover serves no useful purpose under the proposed operating regime and will be removed and replaced with plain track.

P0581 – 23.50km

5.4.4	Bridges and Culverts

There a five bridge structures in this line section.

Based on the structural assessment of bridge beams, the beams in the following bridges are considered inadequate for 19tal under the upgraded operating regime.

3.498km 	2-4.55m span transom deck on steel beams and concrete abutments. Replace with 4-2400 x 2100 RCB

4.298km 	1-4.71m span transom deck on steel beams and concrete abutments. Renew transoms. Replace with 2-2400 x 2100 RCB

It is proposed that the following bridges with timber substructures be replaced.

10.813	4-4.57m span transom deck on steel beams with a timber substructure to replace with 10-2400 x 1500 RCB

15.791km 	4-4.57m span transom deck on steel beams with a timber substructure to replace with 7-2700 x 1500 RCB

21.979km 	1-6.70m span – not located but assumed to be a transom deck on steel beams with a timber substructure to replace with 2-2400 x 1500 RCB

There are 44 culverts listed in this line section. None are load rated.

Where the earth cover can be identified and is greater than 750mm, the culverts are deemed structurally adequate for the upgraded operating regime. They may require either pipe length extension to accommodate the widened formation shoulders, or have ballast retaining beams installed to retain the widened formation shoulders.

17 culverts are recommended for replacement.

The proposed treatment of each culvert is specified in Appendix 6.

5.4.5	Level Crossings

Level crossings in this line section are summarised in the Table.

| TYPE | PROTECTION | NUMBER |
| --- | --- | --- |
| Public sealed | Active | 3 |
| Public sealed | Passive | 2 |
| Public unsealed | Passive | 3 |
| Private/occupation | Passive | 8 |

2 of the public sealed crossings near Narrogin are constructed with 41kg and 50kg rail respectively. These 2 crossings fall outside the section of track which will require upgrading and can be retained. The others are 60lb or 63lb with a variety of 1:4 steel/pandrol plated or plain timber.

The condition of the sealed road surfaces is variable but generally good to fair condition.

All road crossings, other than the 2 near Narrogin, will be upgraded to 41kg rail on concrete sleepers in metal ballast. Drainage improvements will be undertaken, and geotextile used to ensure to ongoing effectiveness of the ballast and drainage.
P0560J – 14.346km

The active protection flashlight crossings, other than Forrest Rd and Pioneer Drive, will need to be recommissioned and allowance has been made in the estimate.

Details of the level crossings are contained in Appendix 5. An ALCAM assessment will likely be required prior to any train operations.

5.4.6	Access to the Track

Between Narrogin and Yilliminning the railway runs through undulating farm land away from the sealed Yilliminning Road. There are only 6 public roads which cross the railway and provide access points. There are also 5 bridges in the line section, indicating that the access along the railway will not be continuous, particularly in wet weather.

Inspections were undertaken by using the public road access points and then the firebreaks as far as was trafficable. The bridge at 10.813km could not be inspected due lack of access.

Access will be created during the process of track upgrading; however, this will not necessarily provide all weather access for road vehicles immediately adjacent to the track. It may be necessary to specify improvements in some sections as part of track upgrading.

At the time of the inspection access would be classified as poor.

5.4.7	Communications

Telstra 3G
The line section has coverage from the Telstra 3G mobile network between Narrogin and Boundain. There are some dark patches. Boundain to Yilliminning is mostly dark with some patches of coverage. There is no coverage at Yilliminning Junction.

Train control must use the train radio network and landlines from Train Order cabins or utilise satellite telephones.

5.4.8	CBH Sidings

There are no primary or secondary CBH sidings in this section.

5.5	Yilliminning (excl) to Corrigin (incl) (85km)

5.5.1	Background

The Yilliminning - Corrigin section became non-operational in June 2014. It was used to transfer 4-6 empty train consist movements per annum between West Merredin and Narrogin at 30km/h under a Train Order system. Gross tonnage Yilliminning to Yealering varied up to 0.5MGTPA.

The last timber resleepering cycle was undertaken in 1991. The section is now generally in poor condition.

5.5.2	Track and Formation

Refer Appendix 1 and Appendix 2.

Rail is primarily 60lb jointed in short lengths.
Sleepers are timber in generally poor condition.
The section is in gravel ballast of good to fair quality. Between 23km and 38km there are sections of metal ballast totalling 11km.

Between Yilliminning and Wickepin, cutting widths are considered adequate. 
Approximately 4km of cuttings will require clean out following track upgrading.

Approximately 4km of banks up to 1.5m will require widening by up to 0.5m each side, and the shoulders of the remaining 12km of banks will require compaction following removal of the gravel ballast.

Between Wickepin and Corrigin, cutting widths are considered adequate. 
Approximately 16km of cuttings will require clean out following track upgrading.

Approximately 20km of banks up to 1.5m will require widening by up to 0.5m each side, and the shoulders of the remaining 29km of banks will require compaction following removal of the gravel ballast.

P0623 – 55.60km

5.5.3	Turnouts

Mainline turnouts at Wickepin are 63lb 1:10 on timber bearers in metal ballast. At the Yilliminning end the turnout is a spring nose similar flexure and is part of the crossover to access the CBH facility. The Corrigin end is SN. They are in fair condition.

It is proposed to establish a new rail siding into the CBH road facility approximately 800m towards Yilliminning. This will make the mainline turnouts in Wickepin redundant. They will be removed and replaced with plain track.

Turnouts at the intermediate CBH siding at Yealering (2) are 63lb 1:10 SN on unplated timber bearers in gravel/metal ballast and at Bullaring (2) are 63lb 1:8 SN on unplated timber bearers in gravel/metal ballast. Condition varies from good to poor. These 2 sidings will be redundant, and the turnouts will be removed and replaced with plain track.

Mainline turnouts at Corrigin are 63lb 1:10 SN on timber bearers in gravel ballast. The turnout to the CBH siding at the Narrogin end is a contra flexure. They are in fair condition.

It is proposed to establish a new rail siding into the CBH road facility approximately 800m towards Narrogin. This will make the mainline turnouts in Corrigin redundant. They will be removed and replaced with plain track.

5.5.4	Bridges and Culverts

There are 15 bridge structures listed on this line section. One was not evident, and it has been deleted.

Based on the structural assessment of bridge beams, the beams in the following bridges are considered inadequate for 19tal under the upgraded operating regime.

25.789km	1-4.57m span transom deck on steel beams with concrete abutments. Replace with 2-2100 x 1500 RCB.

44.533km	1-4.57m span transom deck on steel beams with concrete abutments. Replace with 3-1500 x 1500 RCB.

46.329km	1-9.40m span transom deck on steel beams with concrete abutments. Replace with 5-1800 x 1800 RCB.

55.577km	4-4.57m span transom deck on steel beams with concrete abutments and piers. Replace with 10-1800 x 900 RCB.

67.804km	4-4.57m span transom deck on steel beams with concrete abutments and piers. Replace with 9-1800 x 1500 RCB.

92.099km	2-4.57m span transom deck on steel beams with concrete abutments and pier. Replace with 6-1200 x 1200 RCB.

Others in the section have either timber decks and/or timber substructures and are considered inadequate long term to meet the operating regime. They are recommended for replacement as below.

23.537km	3-4.57m span double track transom deck on steel beams with a timber substructure. Replace with 5-2400 x 1500 RCB

27.879km	4-3.5m spans ballasted timber deck on continuous steel beams with concrete abutments and piers. Replace with 8-1500 x 1200 RCB

P0587

28.945km	3-3.1m spans ballasted timber deck on continuous steel beams with concrete abutments and piers. Replace with 5-1500 x 900 RCB

30.675km	1-5.5m span ballasted timber deck on steel beams with concrete abutments. Replace with 3-1500 x 900 RCB.

33.421km	1-3.0m span ballasted timber deck on steel beams with concrete abutments. Replace with 3-1500 x 900 RCB. Replace with 1-2700 x 2700 RCB

35.813km	2-3.0m spans ballasted timber deck on continuous steel beams with concrete abutments and pier. Replace with 4-1500 x 600 RCB

39.533km	No access for inspection but from bridge asset register it is likely to be
1-3.0m span ballasted timber deck on continuous steel beams with concrete abutments. Replace with 1-2500 x 1500 RCB

39.675km	There is no data recorded for this bridge and it was not located during site inspection. Assumed removed.

107.393km	3-3.0m ballasted timber deck on continuous steel beams with concrete abutments and piers. Replace with 3-2400 x 1500 RCB.

There are 181 culverts listed in this line section. 4 only are load rated for M250. They may require pipe length extension to accommodate the widened formation shoulders, or have ballast retaining beams installed to retain the widened formation shoulders.

Of the others, where the earth cover can be identified and is greater than 750mm, the culverts are deemed structurally adequate for the upgraded operating regime. They may require either no work, pipe length extension to accommodate the widened formation shoulders, or have ballast retaining beams installed to retain the widened formation shoulders.

69 culverts are recommended for replacement.

The proposed treatment of each culvert is specified in Appendix 6.

5.5.5	Level Crossings

Level crossings in this line section are summarised in the Table.

| TYPE | PROTECTION | NUMBER |
| --- | --- | --- |
| Public sealed | Active | 2 |
| Public sealed | Passive | 6 |
| Public unsealed | Passive | 22 |
| Private/occupation | Passive | 19 |

Crossings are 60lb or 63lb with a variety of pandrol plated timber or plain timber sleepers.

The condition of the sealed road surfaces is variable but generally fair to poor condition

All road crossings will be upgraded to 41kg rail on concrete sleepers in metal ballast. Drainage improvements will be undertaken, and geotextile used to ensure to ongoing effectiveness of the ballast and drainage.

All active protection flashlights will need to be recommissioned and allowance has been made in the estimate.

Details of the level crossings are contained in Appendix 5. An ALCAM assessment will likely be required prior to any train operations.

5.5.6	Access to the Track

Yilliminning to Wickepin

Between Yilliminning and Wickepin, the railway runs through undulating farm land away from the main sealed roads. The main sealed road crosses the railway at 6 points. There are 20 public unsealed roads which cross the railway and provide access points. There are also 9 bridges in this section, indicating that the access along the railway will not be continuous, particularly in wet weather.

Inspections were undertaken by using the public road access points and then the firebreaks as far as was trafficable. A few assets required an approach from opposite sides. At the time there had not been recent rain.

Access will be created during the process of track upgrading, however, this will not necessarily provide all weather access for road vehicles immediately adjacent to the track. It may be necessary to specify improvements in some sections as part of track upgrading.

At the time of the inspection access over this section would be classified as poor.

Wickepin to Corrigin

Between Wickepin and Corrigin, the railway runs through farmland away from the main sealed roads. The topography is generally flatter than the previous section. There is only 1 bridge in this section, reflecting the topography. The main sealed road crosses the railway at 6 locations and there are 20 public unsealed roads which cross the railway and provide access points. Over a much of the section a public unsealed road runs parallel to the railway on the north east side. This provides satisfactory access in most weather conditions.

At the time of the inspection access over this section would be classified as satisfactory.

5.5.7	Communications

Telstra 3G

The first 10km from Yilliminning Junction has approximately 50% coverage. The last 10km into Wickepin has full coverage.
There is good coverage for 5km north of Wickepin and 5km south of Yealering. The 15km in between has patchy coverage over 50%.

There is good coverage for 8km north of Yealering but the last 8km into and including Bullaring is dark.
From Bullaring to approximately 10km from Corrigin has about 50% patchy coverage. There is coverage in the Corrigin area.

Train control must use the train radio network and landlines from Train Order cabins or utilise satellite telephones.

5.5.8	CBH Sidings

Refer Appendix 3

Wickepin

The existing CBH facility at Wickepin is located on a dead end siding, set up for drift loading using a shunting tractor. This is not an operation which is viable under present handling practices.

P0607 – Wickepin Dead ends

Standing room for empty wagons is currently restricted to a total of 320m over 2 dead end tracks. This could be increased to 360m by extending each dead end by 20 m. Extension will require a retaining wall to support the CBH access road and barriers to protect the cutting. It still falls well short to the standard train consist length of 500m and requires the train consist to be split for loading.

The existing loop in Wickepin would have to be used as a run-around for the departing loaded trains. Current standing room is only 300m and it will need to be extended 200m towards Corrigin to accommodate a standard consist. Extension could be limited to 60m as 360m is the maximum train consist which could be loaded at Wickepin. 

The option to extend the existing train loading facility is not considered viable.

The proposal is to use the railway reserve land to the south of Wickepin (at approx. 41.70km) along the tangent track between curves adjacent to the CBH road facility and construct a new loading siding. Rail loading facilities will need to be established by CBH. Extension of the existing loop at Wickepin would not then be required and the mainline turnouts will be removed.

Corrigin

The existing CBH facility at Corrigin is located on a dead end siding set up for drift loading using a shunting tractor. This is not an operation which is viable under present handling practices.

P0654 – Corrigin CBH Dead end

Standing room for empty wagons is currently restricted to a total of 200m in a single dead end track in a 2.5m cutting. Any increase in standing room will require cutting under the Corrigin South Rd requiring a bridge, and 300m of land resumption. The existing loop at Corrigin would require extension to provide run-around facilities for a standard consist. Extension of the existing loading facility is not considered realistic or practicable.

The proposal is to use the railway reserve land to the south of Corrigin (at approx. 106.50km) along the tangent track between curves adjacent to the CBH road facility and construct a new loading siding. Rail loading facilities will need to be established by CBH.

5.6	Corrigin (excl) to Bruce Rock (excl) (60km)

5.6.1	Background

The Corrigin – Bruce Rock section became non-operational in June 2014. It was used to transfer 4-6 empty train consist movements per annum between West Merredin and Narrogin at 30km/h under a Train Order system. MGTPA is unknown.

The last timber resleepering cycle was undertaken in 1991. The section is now generally in poor condition.

5.6.2	Track and Formation

Refer Appendix 1 and Appendix 2.

Rail is primarily 60lb jointed in short lengths.
Sleepers are timber with isolated sections of random steel insertions. Timber sleepers are generally in poor condition.
The section is gravel ballast of good/fair quality. Between 137km and 168km there are 3 sections of metal ballast totalling 14km.

P0657 – 121.12km

Cutting widths are considered adequate over the entire line section. 
Approximately 15km of cuttings will require clean out following track upgrading.

Approximately 3km of banks up to 1.5m will require widening by up to 0.5m each side, and the shoulders of the remaining 42km of banks will require compaction following the grading out of the gravel ballast.
There is a section of 3 minor washouts over 20m at the 135.75km.

5.6.3	Turnouts

At Ainsworth, the mainline turnouts are 63lb 1:10 SN on 1:4 steel/timber in gravel ballast. They are in fair condition. Both will be replaced to meet the proposed operating regime. At the Corrigin end the turnout location will be moved approximately 150m towards Corrigin to provide 500m of standing room.

The intermediate CBH siding at Ardath will be redundant. The mainline turnouts (2) are 63lb 1:10 SN on 1:4 steel/timber bearers in metal ballast. Both are in good condition. They will be removed and replaced with plain track.

5.6.4	Bridges and Culverts

There are no bridge structures in this line section.

There are 131 culverts listed in this line section. 3 only are load rated for M250. They may require pipe length extension to accommodate the widened formation shoulders, or have ballast retaining beams installed to retain the widened formation shoulders.

Of the others, where the earth cover can be identified and is greater than 750mm, the culverts are deemed structurally adequate for the upgraded operating regime. They may require either no work, pipe length extension to accommodate the widened formation shoulders, or have ballast retaining beams installed to retain the widened formation shoulders.

45 culverts are recommended for replacement.

Piers on the culvert at 157.30km are significantly eroded and despite the relatively new precast spans it will need to be replaced

P0679 – 157.30km

The proposed treatment of each culvert is specified in Appendix 6.

5.6.5	Level Crossings

Level crossings in this line section are summarised in the Table.

| TYPE | PROTECTION | NUMBER |
| --- | --- | --- |
| Public sealed | Active | 2 |
| Public sealed | Passive | 9 |
| Public unsealed | Passive | 6 |
| Private/occupation | Passive | 12 |

The 2 active protection level crossings are 80lb and 82lb on plain timber sleepers. Other crossings are 60lb or 63lb primarily on plain timber sleepers.

The condition of the sealed road surfaces is variable but generally fair to poor condition

All road crossings will be upgraded to 41kg rail on concrete sleepers in metal ballast. Drainage improvements will be undertaken, and geotextile used to ensure to ongoing effectiveness of the ballast and drainage.

All active protection flashlights will need to be recommissioned and allowance has been made in the estimate.

Details of the level crossings are contained in Appendix 5. An ALCAM assessment will likely be required prior to any train operations.

5.6.6	Access to the Track

North from Corrigin the main sealed road follows the railway to Babakin, then there is a combination of sealed and unsealed local roads following the railway as far as Ardath. The railway then deviates through a section of approximately 5km through farmland and crosses a floodplain before Bruce Rock. The access road has been built up over parts of this floodplain, however, this was only just accessible despite there not being any recent rain.

At the time of the inspection access over this section would be classified as satisfactory, other than the 5km across the floodplain which is fair (dry) to poor (wet).

5.6.7	Communications

Telstra 3G
This section has good overall coverage from the Telstra 3G network, apart from 10 km between Bilbarin and Babakin which has 60% patchy coverage. This patchy coverage area includes Ainsworth CBH.

Train control must use the train radio network and landlines from Train Order cabins or utilise satellite telephones.

5.6.8	CBH Sidings

Refer Appendix 3

Ainsworth

It has been assumed that grain loaded at Ainsworth will be hauled to West Merredin.

Ainsworth is currently configured for drift loading operations using a shunting tractor. This is not an operation which is viable under present handling practices.

There is currently insufficient standing room to provide run-around for the train consist. The siding needs to be extended by approximately 150m towards Corrigin. This will require the existing dead end to be removed so that the formation can be regraded to meet the mainline at a new turnout. 

The CBH loading chute is over the loop line. The train consist will pull into the loop, run-around with the loco and then push back onto the mainline at the south end to commence loading.

Mainline turnouts at either end are 63lb 1:10 SN on timber in gravel ballast and will be replaced. The dead end at the north end can be retained for crippled wagon storage, however, the 63lb 1:10 SN turnout will need to be replaced.

5.7	Bruce Rock (incl) to West Merredin (incl) (48km)

5.7.1	Background

The Bruce Rock – West Merredin section became non-operational in June 2014. It last operated at 16tal at 30kph loaded under a Train Order system. Gross tonnage varied up to 0.7MGTPA.

The last timber resleepering cycle was undertaken in 1997. The section is now generally in poor/fair condition.

5.7.2	Track and Formation

Refer Appendix 1 and Appendix 2.

Rail is 60lb in short jointed lengths.
Sleepers are nominally 1:4 steel/unplated timber sleepers which have been adjusted for rail joints. Joints have 4 timber sleepers each side. Timber sleepers are in fair condition.
The entire section is in metal ballast but fouled in many locations.

P0696 – 170.80km

Cutting widths are considered adequate over the entire line section. 
Approximately 7km of cuttings will require clean out following track upgrading.

Approximately 7km of banks up to 1.5m will require widening by up to 0.5m each side, and the shoulders of the remaining 34km of banks will require compaction following removal of the gravel ballast.

In 3 locations totalling 200m, in banks up to 1m, the formation has been washed away and will require rebuilding.

P0716 – 196.2km to 196.35km

5.7.3	Turnouts

The mainline turnouts at Bruce Rock (3) are 63lb 1:10 SN on timber bearers in metal ballast. They are in poor to fair condition. The CBH facility is on a dead end spur line siding. As 500m of standing room is to be provided within the siding, the crossing loop at Bruce rock is redundant, other than to provide storage for crippled wagons. On this premise, these 3 turnouts will be replaced.

Within the CBH siding, the 2 turnouts are 60lb 1:10 SN and 63lb 1:10 SN respectively on timber bearers in gravel ballast. The 60lb turnout is in good condition, the other is poor. They will both be replaced to meet the proposed operating regime. At the dead end the turnout location will be moved approximately 250m east to provide 500m of standing room.

The intermediate CBH siding at Korbelka will be redundant. The 2 mainline turnouts are 63lb 1:10 SN on timber bearers with some random steel bearers in metal ballast. They are in fair condition. Both will be removed and replaced with plain track.

Turnouts at West Merredin are addressed in Section 5.13.

5.7.4	Bridges and Culverts

There are no bridge structures in this line section.

There are 117 culverts listed in this line section.

83 are load rated for M250. They may require pipe length extension to accommodate the widened formation shoulders, or have ballast retaining beams installed to retain the widened formation shoulders.

Of the others, where the earth cover can be identified and is greater than 750mm, the culverts are deemed structurally adequate for the upgraded operating regime. They may require either no work, pipe length extension to accommodate the widened formation shoulders, or have ballast retaining beams installed to retain the widened formation shoulders.

21 culverts are recommended for replacement.

The proposed treatment of each culvert is specified in Appendix 6.

5.7.5	Level Crossings

Level crossings in this line section are summarised in the Table.

| TYPE | PROTECTION | NUMBER |
| --- | --- | --- |
| Public sealed | Active | 3 |
| Public sealed | Passive | 8 |
| Public unsealed | Passive | 9 |
| Private/occupation | Passive | 11 |

Crossings are 60lb or 63lb rail with a variety of pandrol plated timber or plain timber sleepers. The Great Eastern Highway crossing at West Merredin is 82lb rail on plated timber sleepers.

The condition of the sealed road surfaces is variable from good to poor condition.

All road crossings will be upgraded to 41kg rail on concrete sleepers in metal ballast. Drainage improvements will be undertaken, and geotextile used to ensure to ongoing effectiveness of the ballast and drainage.

All active protection flashlights will need to be recommissioned and allowance has been made in the estimate.

Details of the level crossings are contained in Appendix 5. An ALCAM assessment will likely be required prior to any train operations.

5.7.6	Access to the Track

North from Bruce Rock the main Bruce Rock-Merredin Road follows the railway for 5km, then a combination of local sealed and unsealed roads run parallel to the railway for most of the remaining section to West Merredin. Reasonable all-weather access is available.

The area is generally a little drier, flatter and sandier than sections further south. Railway access roads/firebreaks are also generally accessible although the northern parts of the railway are prone to washaways which would impact access.

At the time of the inspection access over this section would be classified as satisfactory.

5.7.7	Communications

Telstra 3G
The section has good coverage for 10km north of Bruce Rock and 15km south of West Merredin. The 25km in-between is patchy and approximately 75% of the length is dark.

Train control must use the train radio network and landlines from Train Order cabins or utilise satellite telephones.

5.7.8	CBH Sidings

Refer Appendix 3

Bruce Rock

The existing CBH facility at Bruce Rock is located on a dead end spur siding set up for drift loading using a shunting tractor. This is not an operation which is viable under present handling practices, however, it can readily be extended to provide 500m standing room to load under power.

P0682 – Bruce Rock CBH Dead end

This will require the existing single line dead end to be extended by approximately 250m. It will be necessary to resume approximately 150m of the adjacent farm paddock to provide a rail corridor.
 
Empty trains from West Merredin will pull directly into the CBH spur, run-around and load under power within the siding. 

Lethlean Street is approximately 300m from the load out chute and will therefore be blocked for a period during loading operations. The duration of the obstruction is dependent on the CBH load out rate. This has not been assessed.

5.8	Yilliminning (excl) to Kulin (incl) (95km)

5.8.1	Background

The Yilliminning - Kulin section became non-operational in June 2014. It last operated at 16tal at 50kph empty and 40kph loaded under a Train Order system. Gross tonnage varied up to 0.45MGTPA.

The last resleepering cycle was undertaken in 1999 establishing a 1:4 steel/timber pattern using predominantly second hand timber sleepers. The section is now generally in fair/poor condition.

5.8.2	Track and Formation

Refer Appendix 1 and Appendix 2.

Between Yilliminning (0.0km) and Dudinin (59km) rail is 60lb jointed short or longer welded.
Sleepers are nominally 1:4 steel/unplated timber which have been adjusted for rail joints. Joints have 4 timber sleepers each side. Timber sleepers are in fair condition.

The section is primarily gravel ballast of good quality. Sections between 0.0km to 4.0km and 36km to 43km and 3 short sections in between are in metal ballast.

From Dudinin to Kulin (95km) rail is 63lb jointed short or longer welded.
Sleepers are nominally 1:4 steel/unplated timber which have been adjusted for rail joints. Joints have 4 timber sleepers each side. Timber sleepers are in fair condition.

The section is primarily gravel ballast of good quality.

Cutting widths are considered adequate over the entire line section. 
Approximately 14km of cuttings will require clean out following track upgrading.

P0538 – 39.50km

66km of banks require no work other than compaction of shoulders after the grading out of gravel ballast. 
Approximately 15km of banks up to 1.5m will require widening by up to 0.5m each side, and the shoulders of the remaining 66km of banks will require compaction following the grading out of the gravel ballast.

5.8.3	Turnouts

At Nomans Lake the CBH siding will remain in its current configuration. The mainline turnouts (2) are 63lb 1:10 SN on timber bearers in metal ballast and are in fair condition. Both will be replaced to accommodate the proposed operating regime.

There are 4 mainline turnouts at Dudinin. 3 are 63lb 1:10 SN on timber bearers in metal ballast.  The turnout at the Yilliminning end is 31kg 1:10 SN. All are in good condition. The crossing loop at Dudinin is redundant and the 2 turnouts will be removed and replaced with plain track. The 2 turnouts to the CBH siding will be replaced to meet the proposed operating regime.

The turnout to the crippled wagon road is 58lb 1:10 SN on timber bearers in gravel ballast. It will be replaced to meet the proposed operating regime.

At Kulin, the track will be retained in its current configuration. The turnout at the Yilliminning end is 82lb 1:10 SN on 1:2 steel/timber bearers in metal ballast. It will be retained. At the Kulin end the 60lb 1:10 SN turnout on timber bearers in metal will be replaced to meet the proposed operating regime.

5.8.4	Bridges and Culverts

There is only one bridge structure in this line section.

73.476km

1-8.76m span transom deck on steel beams with concrete abutments. 
There is anecdotal advice that this bridge has been previously assessed as structurally inadequate, although it appears sound visually.
Recommended to replace with 3-2400 x 2100 RCB.

P0519

There are 206 culverts listed in this line section.

5 are load rated for M250. They may require pipe length extension to accommodate the widened formation shoulders, or have ballast retaining beams installed to retain the widened formation shoulders.

Of the others, where the earth cover can be identified and is greater than 750mm, the culverts are deemed structurally adequate for the upgraded operating regime. They may require either no work, pipe length extension to accommodate the widened formation shoulders, or have ballast retaining beams installed to retain the widened formation shoulders.

134 culverts are recommended for replacement.

The proposed treatment of each culvert is specified in Appendix 6.

5.8.5	Level Crossings

Level crossings in this line section are summarised in the Table.

| TYPE | PROTECTION | NUMBER |
| --- | --- | --- |
| Public sealed | Active | 3 |
| Public sealed | Passive | 6 |
| Public unsealed | Passive | 19 |
| Private/occupation | Passive | 29 |

Public sealed crossings are 80lb or 63lb on 1:4 steel/pandrol plated timber or plain plated timber sleepers.

The condition of the sealed road surfaces is variable but generally fair to poor condition.

All road crossings will be upgraded to 41kg rail on concrete sleepers in metal ballast. Drainage improvements will be undertaken, and geotextile used to ensure to ongoing effectiveness of the ballast and drainage.

All active protection flashlights will need to be recommissioned and allowance has been made in the estimate.

Details of the level crossings are contained in Appendix 5. An ALCAM assessment will likely be required prior to any train operations.

5.8.6	Access to the Track

From Yilliminning to the Yilliminning Road crossing at 18.8km the railway passes through open farmland where the only access is on the railway access road/firebreak. There are only 4 public road access points to the railway. Despite there not being any recent rain, this access was poor.

From the Yilliminning Road crossing the main road follows the railway to Toolibin, then there is an unsealed public road (Line Rd) which follows the railway to Harrismith. Access between Harrismith and Dudinin is along reasonably well-established railway access tracks/firebreaks. There are 16 public road access points between Nomans Lake and Dudinin.

The main sealed road follows the railway (20 – 100m) between Dudinin and Jitarning and for another 11km beyond.

The last 9km to Kulin passes through farmland accessible only along the railway access road/firebreak. This will not provide all weather access although it is drier than the earlier parts of the section. There are only public road access points in this section.

At the time of the inspection, access for the first 20km was poor, and the remainder would be classified as satisfactory.

5.8.7	Communications

Telstra 3G
Yilliminning Junction to Tincurrin (40km) is almost all dark apart from short, patchy coverage areas.
Tincurrin to Dudinin (19km) has coverage except for the last 3-4km into and including Dudinin which is dark.
Dudinin to Kulin (36km) has approximately 40% coverage in long patches. The last 5km to Kulin is covered.

Train control must use the train radio network and landlines from Train Order cabins or utilise satellite telephones.

5.8.8	CBH Sidings

Refer Appendix 3

Nomans Lake

The existing standing room on the Nomans Lake CBH siding is approximately 590m. The loading chute is in the middle of the siding.
There is approximately 510m between the loading chute and Nomans Lake Siding Road at the Narrogin end which is just sufficient to ensure train loading without blocking the crossing.
Other than track upgrading and replacement of the mainline turnouts, no works are required.

Dudinin

The existing standing room on the Dudinin CBH siding is approximately 510m which is just adequate to provide run-around room for the train consist. The 2 loading chutes span the middle of the siding.
There is approximately 320m standing room between the Kulin end loading chute and Fence Road and consequently this level crossing will be blocked for a period during train loading. Fence Rd is the principal access for the township off Dudinin-Jitarning Rd. There appears no reasonable alternative detour. It is likely that new crossing access of Fence Rd from the Dudinin-Jitarning Rd will need to be constructed with approximately 550m standing room from the loading chute. 
A short section of the back road can be retained as crippled wagon storage. The turnout will be replaced.
Mainline turnouts to the crossing loop on the DN side can be removed and replaced with plain track.

Jitarning

At the Yilliminning end the turnout is 63lb 1:10 SN on timber/random steel bearers in gravel ballast. The Kulin end is 63lb 1:10 SN on timber/random steel bearers in gravel ballast. This is a similar flexure turnout.
This siding is redundant and the 2 mainline turnouts will be removed and replaced with plain track.

Kulin

Train loading at Kulin is essentially on the mainline with the run-around loop on the DN side. Standing room for loco run-around is approximately 1050m and there is adequate standing room for empty wagons during loading.
There is only 370m between the loading chute and Jilakin Rd at the Narrogin end. This is the only access in and out of the CBH facility from the N side of the railway and it will be blocked for a period during loading.
The turnout at the Narrogin end is 82lb 1:10 SN on 1:2 steel timber in metal ballast and can be retained. The turnout at the Kulin end only 60lb on timber and it will be replaced.
Other than track upgrading, no other work is required.

5.9	Kondinin (incl) to Narembeen (excl) (51km)

5.9.1	Background

The Kondinin - Narembeen section became non-operational in June 2014. It last operated at 16tal at 30kph loaded under a Train Order system. Gross tonnage varied up to 0.35MGTPA.

The last resleepering cycle was undertaken in 1999 establishing a 1:4 steel/timber pattern using predominantly second hand timber sleepers. The section is now generally in fair/poor condition.

5.9.2	Track and Formation

Refer Appendix 1 and Appendix 2.

Rail is 60lb in jointed 60m lengths of LWR.
Sleepers are nominally 1:4 steel/unplated timber sleepers which have been adjusted for rail joints. Joints have 4 timber sleepers each side. Timber sleepers are in fair condition.
The section is metal ballast from Kondinin (118km) to the 121km; 146km to 149km; and 162km to 169km (Narembeen). The remainder is gravel ballast of generally good quality.

P0752 – 121.30km

Cutting widths are considered adequate over the entire line section. 
Approximately 7km of cuttings will require clean out following track upgrading.

Approximately 8km of banks up to 1.5m will require widening by up to 0.5m each side, and the shoulders of the remaining 36km of banks will require compaction following grading out of the gravel ballast.

Formation has been washed away in 4 locations totalling 900m and will require rebuilding.

5.9.3	Turnouts

There are 3 mainline turnouts at Kondinin. At the Kulin end the turnout is 60lb 1:10 spring nose on timber bearers in gravel ballast. The intermediate turnout is 63lb 1:10 SN on 1:4 steel/timber bearers in gravel ballast. At the Narembeen end the turnout is 63lb 1:10 SN on timber bearers in gravel ballast. They are in poor to fair condition. 

As it is proposed to establish a new CBH siding approximately 2.5km on the Narembeen side, the sidings in Kondinin are redundant unless retained for wagon storage. These turnouts should be retained in track as non-operational.

At South Kumminin there are 2 mainline turnouts. 1 is 63lb 1:10 SN on 1:2 steel/timber bearers in metal ballast and is in excellent condition. The other is 63lb 1:10 SN on timber bearers in gravel ballast with random steel bearers and is in fair condition. Both turnouts will be replaced to meet the proposed operating regime. The turnout at the Narembeen end will be moved approximately 220m towards Narembeen to provide 500m standing room.

The intermediate CBH siding at Bendering will be redundant. The 2 mainline turnouts are both 63lb 1:10 SN on 1:4 steel/timber in gravel ballast. They are in fair condition but will be removed and replaced with plain track.

5.9.4	Bridges and Culverts

There are no bridge structures in this line section

There are 103 culverts listed in this line section. None are load rated.

Where the earth cover can be identified and is greater than 750mm, the culverts are deemed structurally adequate for the upgraded operating regime. They may require either no work, pipe length extension to accommodate the widened formation shoulders, or have ballast retaining beams installed to retain the widened formation shoulders.

62 culverts are recommended for replacement.

The proposed treatment of each culvert is specified in Appendix 6.

5.9.5	Level Crossings

Level crossings in this line section are summarised in the Table.

| TYPE | PROTECTION | NUMBER |
| --- | --- | --- |
| Public sealed | Active | 2 |
| Public sealed | Passive | 5 |
| Public unsealed | Passive | 9 |
| Private/occupation | Passive | 13 |

Public sealed crossings are primarily 60lb or 63lb on plated timber sleepers. The Mt Walker Rd at Narembeen is 82lb on plated timber sleepers.

The condition of the sealed road surfaces is variable but generally fair to poor condition.

All road crossings will be upgraded to 41kg rail on concrete sleepers in metal ballast. Drainage improvements will be undertaken, and geotextile used to ensure to ongoing effectiveness of the ballast and drainage.

The active protection flashlight crossings will need to be recommissioned and allowance has been made in the estimate. The Kondinin-Narembeen Rd at 126.8km has a flashlight mast on one side only. The other side has been removed during road widening works.

Details of the level crossings are contained in Appendix 5. An ALCAM assessment will likely be required prior to any train operations.

5.9.6	Access to the Track

An unsealed public road follows the railway for the first 9km north of Kondinin where it then meets the main sealed Narembeen Rd. This sealed road closely follows the railway to South Kumminin where it then deviates away for approximately 10km and access is then restricted to the railway access road/firebreak. From there to Narembeen the railway follows the main sealed Narembeen Rd.

At the time of inspection access would be generally classified as satisfactory.

5.9.7	Communications

Telstra 3G
Kondinin to approximately 9km south of South Kumminin has coverage. The 9km to South Kumminin is dark.
South Kumminin (incl) to Narembeen has coverage.

Train control must use the train radio network and landlines from Train Order cabins or utilise satellite telephones.

5.9.8	CBH Sidings

Refer Appendix 3

Kondinin

The old CBH rail loading facility in Kondinin does not appear to be in use with a road truck operation.

A new road transfer facility has been established by CBH approximately 2500m on the West Merredin side of Kondinin. It is proposed that a new rail loading siding be constructed into this facility. This will require 2 new mainline turnouts and approximately 700 – 800m of new siding formation, drainage and track. Rail loading facilities will need to be established by CBH.

P0750 – 121.30km

It is recommended that no work be undertaken in the existing Kondinin yard and CBH facility.

South Kumminin

South Kumminin is currently configured for drift loading operations using a shunting tractor. This is not an operation which is viable under present handling practices.

There is currently insufficient standing room to provide run-around for the train consist. The siding needs to be extended by approximately 220m towards Narembeen to provide this. The train consist will then block the north end CBH access during run-around and in the latter stages of train loading. There is alternate access at the S end.

The existing dead end siding will need to be extended by approximately 250m on a 1.5m embankment to provide 500m standing room for the empty wagons prior to loading. 
The CBH loading chute is over the loop line. The train consist will pull into the loop, run-around with the loco and then push back south into the dead-end siding to commence loading.

The 2 mainline turnouts are 63lb 1:10 SN on 1:4 steel/timber in gravel ballast and will be replaced. The dead end siding turnout 63lb 1:10 SN on timber bearers in gravel ballast will need to be replaced.

5.10	Narembeen (incl) to West Merredin (incl) (91km)

5.10.1	Background

The Narembeen – West Merredin section became non-operational in June 2014. It last operated at 16tal at 30kph loaded under a Train Order system. Gross tonnage varied up to 0.9MGTPA.

The last resleepering cycle was undertaken in 1997 establishing a 1:4 steel/timber pattern using predominantly second hand timber sleepers. The section is now generally in fair/poor condition.

5.10.2	Track and Formation

Refer Appendix 1 and Appendix 2

Track is 60lb in jointed 60m LWR.
Sleepers are nominally 1:4 steel/unplated timber sleepers which have been adjusted for rail joints. Joints have 4 timber sleepers each side. Timber sleepers are in fair condition.

The entire section is in metal ballast although heavily fouled in some sections.

P0796 - 203.40km Cramphorne Rd.

Cutting widths are considered adequate over the entire line section. 
Approximately 13km of cuttings will require clean out following track upgrading.

Approximately 1km of banks up to 1.5m will require widening by up to 0.5m each side, and the shoulders of the remaining 76km of banks will require compaction following grading out of the gravel ballast.

Formation in banks 1-1.5m has been washed away in 2 locations totalling 650m and will require rebuilding.

P0807F – 244.75km to 245.20km

5.10.3	Turnouts

There are 3 mainline turnouts currently in Narembeen.

The 2 turnouts to the loop are 63lb 1:10 SN in metal ballast. At the Kondinin end the turnout is on timber bearers. The West Merredin end is on 1:4 steel timber bearers. The loop will become redundant, so both these turnouts will be removed and replaced with plain track.

The turnout to the CBH siding is 82lb 1:10 CM on 1:4 steel/timber in metal ballast. It is in fair condition. It should be upgraded to 1:2 steel/timber bearers and retained.

There are 4 mainline turnouts at Muntadgin serving 2 adjacent CBH facilities. 2 are 63lb 1:10 SN on timber bearers in metal ballast. 1 is 63lb 1:10 SN on 1:4 steel/timber bearers in metal ballast and the other is 63lb 1:10 SN on 1:2 steel/timber bearers in metal ballast.

Under the proposed reconfiguration, 2 of the intermediate turnouts are redundant and they will be removed and replaced with plain track. The 2 turnouts at the extremities will be replaced to meet the proposed operating regime. At the West Merredin end one of these will be relocated approximately 30m towards West Merredin to provide a new connection to the mainline.

Intermediate CBH sidings at Wogarl and Koonadgin are redundant and the turnouts will be removed and replaced with plain track. All are 63lb 1:10 SN on 1:2 or 1:4 steel/timber bearers in metal ballast and in fair condition.

Turnouts at West Merredin are addressed in Section 5.13.

5.10.4	Bridges and Culverts

There are no bridge structures in this line section

There are 149 culverts listed in this line section.

91 are load rated for M250. They may require pipe length extension to accommodate the widened formation shoulders, or have ballast retaining beams installed to retain the widened formation shoulders.

Of the others, where the earth cover can be identified and is greater than 750mm, the culverts are deemed structurally adequate for the upgraded operating regime. They may require either no work, pipe length extension to accommodate the widened formation shoulders, or have ballast retaining beams installed to retain the widened formation shoulders.

43 culverts are recommended for replacement.

The proposed treatment of each culvert is specified in Appendix 6.

5.10.5	Level Crossings

Level crossings in this line section are summarised in the Table.

| TYPE | PROTECTION | NUMBER |
| --- | --- | --- |
| Public sealed | Active | 3 |
| Public sealed | Passive | 10 |
| Public unsealed | Passive | 21 |
| Private/occupation | Passive | 15 |

Public sealed crossings are 63lb or 60lb on 1:4 steel sleepers/pandrol plated timber sleepers or plain plated timber sleepers in metal ballast. The public sealed level crossing at 171.7km is a new crossing following road realignment. It is constructed in 41kg on concrete sleepers and requires no work.

The Great Eastern Highway, Mary St and Barrack St crossings in Merredin are 82lb. The SG EGR runs parallel alongside the NG at Mary St and Barrack St.

P0807J – 255.60km Mary St

The condition of the sealed road surfaces is variable from poor to good condition.

All road crossings will be upgraded to 41kg on concrete sleepers in metal ballast. Drainage improvements will be undertaken, and geotextile used to ensure to ongoing effectiveness of the ballast and drainage.

The active protection flashlight crossings will need to be recommissioned and allowance has been made in the estimate. In the case of the new level crossing at 171.8km, it currently has no protection. The protection level will need to be assessed but is assumed to require active protection.

Details of the level crossings are contained in Appendix 5. An ALCAM assessment will likely be required prior to any train operations.

5.10.6	Access to the Track

From Narembeen to Muntadgin a public sealed/unsealed road follows the railway except for 1 short section of 4 km where the only access is the railway access track/firebreak.

Unsealed Scott Rd then follows the railway to approximately 3km north of Koonadgin.

From this point to Merredin access is primarily only along the railway access road/firebreak which is difficult and subject to wash away.

At the time of inspection access would be classified as satisfactory, apart from Koonadgin to Merredin which was poor.

5.10.7	Communications

Telstra 3G
Narembeen to Wogarl has coverage. There are a couple of dark patches in the last 5km to Wogarl.
Wogarl to Muntadgin has coverage apart from a couple of short dark patches around Wogarl and Cramphorne.
Muntadgin to Tandegin (10km) has coverage. Tandegin to Koonadgin (10km) is dark.
Koonadgin to Norpa is mostly dark except for approximately 3-4km in the middle section.
Norpa to West Merredin has coverage

Train control must use the train radio network and landlines from Train Order cabins or utilise satellite telephones.

5.10.8	CBH Sidings

Refer Appendix 3

Narembeen

Narembeen CBH is currently configured for drift loading operations using a shunting tractor. Standing room for loading is limited to 220m. This is not an operation which is viable under present handling practices.

Extension of the CBH facility for 500m train consists is problematic due to the proximity and alignment of the Narembeen-Merredin Road.

It is proposed to connect the existing dead-end siding to the mainline at the West Merredin end such that it crosses the Narembeen-Merredin Rd just on the Narembeen side of the CBH access road. This provides approximately 590m of standing room between the 2 Narembeen-Merredin Rd crossings to run around the train consist without blocking the roads. The dead end siding will then be extended approximately 380m on a curved alignment which follows the Narembeen-Merredin Rd to provide 500m of standing room for empty wagons prior to loading. This extension will cross the CBH access road and will require some minor land resumption.

The empty consist will pull into the CBH siding at the West Merredin end, then set the empty wagons back into the extended dead end to commence loading. During the early period of loading the CBH access road will be blocked. During the later period of loading the Narembeen-Merredin Rd at the Narembeen end will be blocked as there is only 340m of standing room between the loading chutes and the road crossing. The duration of the obstruction will be dependent on the CBH load out rate. This has not been assessed.

The turnout to CBH at the Narembeen end is 82lb 1:10 cast manganese on 1:4 steel/timber in metal ballast and can be retained.
There is no reason to retain the Narembeen crossing loop, so those mainline turnouts could be removed and replaced with plain track.

Muntadgin

There are 2 CBH facilities at Muntadgin both with rail sidings, although the facility at the Narembeen end does not have dedicated rail loading facilities. The older facility is currently configured for drift loading operations using a shunting tractor. Standing room for loading is limited to 250m maximum. This is not an operation which is viable under present handling practices.

The existing configuration can be rationalised. It is proposed to connect the existing dead end siding at the West Merredin end to the mainline with a new turnout.  The siding formation will need to be lowered to match the mainline. 

The existing dead end siding at the Narembeen end will be extended by approximately 130m to connect to the southern loop. A 6-600 RCP will need to be extended under the new track. This will provide run-around standing room of 1100m and remove 2 mainline turnouts and 2 siding turnouts.

The CBH access road at the West Merredin end will be blocked in the latter stages of train loading, however, there is road access at the Narembeen end.

5.11	Katanning (excl) to Nyabing (incl) (61km)

5.11.1	Background

The Katanning - Nyabing section became non-operational in 2008. It last operated at 16tal at 30kph loaded under a Train Order system. Gross tonnage varied up to 0.1MGTPA.

The last resleepering cycle was undertaken in 1980. The section is now generally in poor condition

5.11.2	Track and Formation

Refer Appendix 1 and Appendix 2

Between the 1.0km and the 6.0km rail is 66kg CWR.
Between 0.0km and 7.0km sleepers are 1:2 steel/timber.
From the 6.0km to Nyabing, rail is primarily 60lb in short or LWR jointed lengths. 
From the 7.0km to Nyabing, sleepers are nominally 1:4 steel/unplated timber which have been adjusted for rail joints. Joints have 4 timber sleepers each side. Timber sleepers are in fair/poor condition.
The section from 0.0km to 35.0km (Badgebup) in metal ballast.

The remainder of the section from the 35.0km to the 61.0km (Nyabing) is in gravel ballast of generally poor quality.

P0957 - 45.10km

Cutting widths are considered adequate over the entire line section. 
Approximately 9km of cuttings will require clean out following track upgrading.

Approximately 9km of bank up to 1.0m will require widening by up to 0.5m each side. 
43km of banks require no work other than compaction of shoulders after the grading out of gravel ballast.

Formation in banks 0.5-1.0m has been washed away in 3 locations totalling 150m and will require rebuilding.

5.11.3	Turnouts

There are 3 turnouts at Katanning on the triangle which are associated with the Nyabing line. The N and S ends link to the GSR and are 82lb 1:10 SN. They will remain. The E end of the triangle is 63lb 1:10 SN on timber bearers in metal ballast and is in good condition. It will be replaced to meet the requirements of the proposed operating regime.

At Nyabing, there are 3 mainline turnouts. 2 are 63lb 1:10 SN on timber bearers in metal ballast. The facing points are 63lb 1:10 SN contra flexure on timber bearers in gravel ballast. It will be relocated towards Nyabing to remove it from the curve. All turnouts will be replaced to meet the proposed operating regime.

The intermediate CBH siding at Badgebup is redundant. The 2 mainline turnouts are 63lb 1:10 SN on timber bearers in gravel ballast. They will be removed and replaced with plain track. Some realignment is required at the Katanning end once the turnout is removed.

5.11.4	Bridges and Culverts

There are 5 bridge structures listed on this line section. 1 has already been replaced by an RCB.

Based on the structural assessment of bridge beams, the beams in the following bridges are considered inadequate for 19tal under the upgraded operating regime.

9.594km	1-5.4m transom deck on steel beams with concrete abutments. Replace with 2-2400 x 1500 RCB

10.083km	15-4.5m span transom deck on steel beams with concrete abutments and piers. Upgrade beams to 19tal, re-transom and add a walkway refuge.

11.380km	10-4.5m span transom deck on steel beams with concrete abutments and piers. Upgrade beams to 19tal, re-transom and add a walkway refuge.

P0973

Of the remaining 2 structures:

16.756km	Already replaced by 2-900 x 900 RCB

19.488km	17-4.5m spans transom deck on steel beams with timber substructure with steel props in 2 spans. It is deemed inadequate for the proposed operating regime. 
Replace with 23-2700 x 1800 RCB

P0968

There are 140 culverts listed in this line section. 22 of those listed could not be located and are assumed to be removed.

2 are load rated for M250. Many others have already been replaced with RCP’s and are assumed to be M250 load rated. They may require pipe length extension to accommodate the widened formation shoulders, or have ballast retaining beams installed to retain the widened formation shoulders.

Of the others, where the earth cover can be identified and is greater than 750mm, the culverts are deemed structurally adequate for the upgraded operating regime. They may require either no work, pipe length extension to accommodate the widened formation shoulders, or have ballast retaining beams installed to retain the widened formation shoulders.

73 culverts are recommended for replacement.

P0956 – OMT 53.69km

The proposed treatment of each culvert is specified in Appendix 6.

5.11.5	Level Crossings

Level crossings in this line section are summarised in the Table. This includes level crossings on the N-E and S-E legs of the triangle.

| TYPE | PROTECTION | NUMBER |
| --- | --- | --- |
| Public sealed | Active | 6 |
| Public sealed | Passive | 5 |
| Public unsealed | Passive | 10 |
| Private/occupation | Passive | 21 |

Public sealed crossings are 60lb, 63lb or 41kg on pandrol plated timber sleepers or plain plated timber sleepers.

The condition of the sealed road surfaces is variable but generally poor to good condition. Bay St at Katanning and Creek St at 0.66km require no upgrade.

All remaining road crossings will be upgraded to 41kg rail on concrete sleepers in metal ballast. Drainage improvements will be undertaken, and geotextile used to ensure to ongoing effectiveness of the ballast and drainage.

All active protection flashlights will need to be recommissioned and allowance has been made in the estimate.

Details of the level crossings are contained in Appendix 5. An ALCAM assessment will likely be required prior to any train operations.

5.11.6	Access to the Track

From Katanning to Langeweira Rd (17km) the railway access track and an unsealed public road (Lake Heuppauff Rd) follow the railway. Between the 9km and 20km, there are 5 bridges. The access road crosses 2 major lake waterways and concrete floodway’s have been provided through the main channels. This provides good access in most weather conditions until such time as a major flood washes out the access.

From Langeweira Rd to Hotker Rd (23km) the railway passes through a series of lake floodplains where the railway access road/firebreak provides partial if unpredictable access. The road at the 19.49km bridge could be washed away at any time making it impassable. From Hotker Rd to Badgebup (35km) the railway passes through farmland where the railway access track/firebreak is relatively poor with limited public access points. Access will be improved during track works, however, some specific upgrading in this section should be considered.

The main sealed Katanning-Nyabing Road then follows the railway to Nyabing.

At the time of inspection, the access would be considered as satisfactory, apart from the section from Langeweira Rd to Badgebup (18km) which is poor.

5.11.7	Communications

Telstra 3G
Katanning to Badgebup (35km) has coverage for 10km out of Katanning and 10km out of Badgebup. There is 15km in-between which is dark.
There is coverage for approximately 10km east of Badgebup and 5km west of Nyabing. The 11km in-between is dark.

Train control must use the train radio network and landlines from Train Order cabins or utilise satellite telephones.

5.11.8	CBH Sidings

Refer Appendix 3


Nyabing

There are 3 rail loading points in the Nyabing CBH facility. The existing run-around loop provides approximately 510m standing room clear of Bin Rd. This allows loco run-around without blocking this road.

At best, there is only 390m of standing room for empty wagons prior to the loading point at the Katanning end. This will then require splitting of the standard train consist between the 2 dead end sidings. Once the first part of the consist is loaded, the train will have to set back and reconnect the remaining empty wagons for loading. 

There is approximately 445m standing room between the Katanning end loading point and Bin Rd. This means Bin Rd will be blocked for loading of the last 2 wagons. There is alternate access on Bin Rd to the east.

The 3 - 63lb 1:10 SN on timber turnouts will be replaced. The mainline turnout at the Katanning end is a contra flexure turnout which will be moved east, closer to Bin Rd, to a straight alignment.

5.12	Tambellup (excl) to Gnowangerup (incl) (38km)

5.12.1	Background

The Tambellup - Gnowangerup section became non-operational in 2008. It last operated at 16tal at 30kph loaded under a Train Order system. Gross tonnage varied up to 0.1MGTPA.

The last resleepering cycle was undertaken in 1999. The section is now generally in poor condition

5.12.2	Track and Formation

Refer Appendix 1 and Appendix 2

Rail is primarily 60lb jointed LWR (24-48m with glued joints)
Sleepers are nominally 1:4 steel/unplated timber which have been adjusted for rail joints. Joints have 4 timber sleepers each side. Timber sleepers are in fair/poor condition.

The section is primarily in gravel ballast. There are 3 locations each around 200m each between 10.0km and 18.0km which are metal ballast.

Cutting widths are considered adequate over the entire line section. 
Approximately 6km of cuttings will require clean out following track upgrading.

Approximately 4km of banks up to 1.0m will require widening by up to 0.5m each side.
28km of banks require no work other than compaction of shoulders after the grading out of gravel ballast.

Formation in bank to 1.0m has been washed away in 1 location of 20m and will require rebuilding.

5.12.3	Turnouts

The turnout at the Tambellup end which connects to the GSR has been removed and remains stacked on site. A new turnout will be reinstated in the GSR to renew the connection.

At Gnowangerup, there are 3 mainline turnouts and 1 in the CBH spur siding. The turnout at the Nyabing end of the loop is 63 1:8 spring nose on timber bearers in gravel ballast and is in poor condition. The turnouts at the Tambellup end of the loop and the CBH spur are both 63lb 1:10 SN on timber bearers in gravel ballast and in fair to poor condition. The turnout in the CBH siding has been sealed over and its configuration could not be established. All will be replaced to meet the proposed operating regime.

5.12.4	Bridges and Culverts

There are 3 bridges in this line section.

0.705km	This is 4-4.57m spans ballasted timber deck on a timber substructure. This is inadequate for the proposed operating regime.
It will be replaced with a 9-1800 x 1800 RCB.

P0924

27.781km	This is 20-4.57m spans ballasted timber deck on a timber substructure with steel support frames for spans 9 and 10. This structure is inadequate for the proposed operating regime.
The bridge will be replaced with a 30-3000 x 2700 RCB.

P0934

36.178km	This is 2-4.57m spans ballasted timber deck with concrete abutments and pier. The substructure is sound.
The superstructure will be replaced with ballasted steel deck spans.

There are 106 culverts listed in this line section. 22 of these could not be located and are assumed to be removed.

None are load rated. Many have already been replaced with RCP’s and are assumed to be M250 load rated. They may require pipe length extension to accommodate the widened formation shoulders, or have ballast retaining beams installed to retain the widened formation shoulders.

Of the others, where the earth cover can be identified and is greater than 750mm, the culverts are deemed structurally adequate for the upgraded operating regime. They may require either no work, pipe length extension to accommodate the widened formation shoulders, or have ballast retaining beams installed to retain the widened formation shoulders.

64 culverts are recommended for replacement.

P0933 – 25.10km

The proposed treatment of each culvert is specified in Appendix 6.

5.12.5	Level Crossings

Level crossings in this line section are summarised in the Table.

| TYPE | PROTECTION | NUMBER |
| --- | --- | --- |
| Public sealed | Active | 1 |
| Public sealed | Passive | 2 |
| Public unsealed | Passive | 9 |
| Private/occupation | Passive | 16 |

Public sealed crossings are 60lb on plain plated timber sleepers.

The condition of the sealed road surfaces is variable in poor to good condition.

All road crossings will be upgraded to 41kg rail on concrete sleepers in metal ballast. Drainage improvements will be undertaken, and geotextile used to ensure to ongoing effectiveness of the ballast and drainage.

All active protection flashlights will need to be recommissioned and allowance has been made in the estimate.

Details of the level crossings are contained in Appendix 5. An ALCAM assessment will likely be required prior to any train operations.

5.12.6	Access to the Track

For the first 5km from Tambellup the railway is adjacent to the main Tambellup Gnowangerup Rd. It then diverges into open farmland most of the way to Gnowangerup. Access is primarily along the railway access road/firebreak with short sections adjacent to sealed/unsealed public roads. There are 9 public road access points through this section. Although the 3 bridges are impediments to continuous access, they are not major constraints due to their location in regard to alternate access.

Apart from the first 5km, at the time of inspection, the access would be considered poor. Access will be difficult in wet weather.

5.12.7	Communications

Telstra 3G
There is coverage for approximately 15km from Tambellup and 5km from Gnowangerup. The 18km in-between is largely dark

Train control must use the train radio network and landlines from Train Order cabins or utilise satellite telephones.

5.12.8	CBH Sidings

Refer Appendix 3

Gnowangerup

The existing run-around loop provides approximately 470m standing room. Given that the train consist at the CBH loading facility will be restricted to 300m there is no requirement to extend this loop.

The CBH spur is a separate facility remote from the run-around loop. At best, there is only 300m of standing room for empty wagons prior to the loading point, split over 2 dead end sidings. This will then require splitting of the standard train consist between the 2 dead end sidings. Once the first part of the consist is loaded, the train will have to set back and reconnect the remaining empty wagons for loading. 

There is approximately 200m standing room between the CBH loading point and Garnett Rd. This means Garnett Rd will be blocked for a period during loading. This is not considered an issue as the main CBH access will still be available and there are alternate routes for local traffic. The turnout in the siding (which has been sealed over) will be replaced.

Extension of the CBH siding dead ends to provide a total of 500m standing room for a standard consist is not considered realistic. Both tracks would extend over Stutley Street into private developed premises. As there is no other established CBH grain handling facility in the area adjacent to the railway, train consists between Tambellup and Gnowangerup will be limited to 300m.

P0943 – Gnowangerup CBH Dead end

A rail loading facility could be established adjacent to the run-around loop at the Tambellup end in Gnowangerup. In that case the loop could be extended by 30m to provide 500m standing room for empty wagons prior to the loading point. Walsh Rd is would be blocked for a period during loading of the last 250m of the train consist. The duration of the obstruction will be dependent on the location and loadout rate at the new CBH loading point. There are alternate routes for local traffic.

5.13	West Merredin Yard

Narrow Gauge Option

Refer to Appendix 7A

The Bruce Rock line NG connection to the CBH loaded inwards yard remain intact. The facing points turnout is 82lb 1:10 SN and will be retained. Standing room for a 500m consist to run-around in the yard appears tight but tracks can readily be extended at the east end to provide additional length if required.

P0863

The Narembeen line NG connection to the CBH loaded inwards yard remain intact. The facing points turnout which diverges the Trayning and Narembeen lines is a 63lb 1:10 SN and will be replaced. The track alignment at the east end can be rationalised by removal of the adjacent crossover and realignment of the combined Narembeen/Trayning lines into the NG CBH loaded inwards yard with upgraded track.

P0860B

The Trayning line has been disconnected from the NG yard by removal of the diamond crossing of the SG EGR. This will need to be reinstated. There is likely to be resistance to this proposal from Arc Infrastructure.  The costs to reinstate interlocked signalling are significant and have been allowed in the estimates.

P0860A

The CBH loaded inwards yard is primarily 80lb (some 63lb) on timber sleepers (some patterned steel) in metal ballast (gravel on approach to the CBH unloading bin). With some resleepering this track structure can be retained. Turnouts are 82lb 1:10 SN on timber bearers in metal ballast and can be retained.

No allowance has been made to refurbish or upgrade the CBH grain wagon discharge facilities.

P0865

The CBH empty outwards yard comprises 3 dead end tracks. There is no opportunity to close the connections back to NG. Empty consists may have to set back into the inwards yard to run-around.

2 of the dead end tracks are 80lb rail on timber sleepers and can be retained with some steel resleepering. The third track (to the left) is used for crippled wagon storage and is 60lb on 1:4 steel/timber sleepers. With some steel resleepering, this can also be retained as fit for this purpose.

The 3 turnouts at this outwards end of the CBH shed are 63lb on timber bearers in gravel ballast and will be replaced by 41kg 1:10 1:4 steel/timber.

P0866

Standard Gauge Option

Refer to Appendix 7B

The schematic diagram does not fully reflect the actual track geometry on site. The EGR alignment is on a curve between the Narembeen connection and the Trayning connection.

To make a SG connection from the Bruce Rock line, the NG CBH loaded inwards sidings will have to be disconnected and partially removed to allow the SG Bruce Rock line to extend to the CBH SG yard to a new turnout on the CBH loading road. The SG sidings at the east end will require approximately 100m extension and a new turnout to provide 500m standing room to run-around the consist. Some operational conflicts could occur on the CBH SG loading road when a Bruce Rock train arrives. This is considered manageable for the proposed operating regime.

The Narembeen SG connection will extend to connect to the SG EGR loop to form a new signal interlocked crossover. Trains will then proceed to the CBH SG yard via the loop. All NG connections to the yard will be removed.

The Trayning SG connection is a little more complex. As the EGR is on a curve, the Trayning connection must be moved west to tangent track on the EGR so that the new turnout and crossover can be installed. The alignment will run parallel to the EGR for approximately 500m between the new EGR connection and Gamenya Ave. Trains can then enter the CBH yard via the loop. These new connections will all require interlocked signalling.

Trains from all 3 lines can then be combined into longer consists in the SG Yard for transit directly to Kwinana.

# Upgraded Track Structure

To meet the operating standard required under this review, 19tal requires a minimum rail size of 80lb/yd. The nearest rail size currently being produced is 41kg/m. Any rail in the Tier 3 lines which is less than 80lb/yd must, therefore, be changed out for new 41kg/m rail. This will all be continuously welded (CWR).

Gravel ballast does not drain the track adequately to ensure sustainable all-weather operation. Therefore, to meet the operating standard, all gravel ballast must be replaced with crushed metal ballast with a minimum depth under the sleeper of 150mm.

There are several sleeper configurations which may be used to support 19tal at 80kph with 41kg/m rail on metal ballast. These include:

- 1:2 steel/timber on standard plates with 2 screw spikes per plate and 2 screw spikes per rail seat with rail anchors in selected areas (as per the existing GSR).

- 1:2 or 1:4 steel/timber with resilient fastenings.

- 1:2 or 1:4 steel/low-profile concrete sleepers.

- All low-profile concrete sleepers.

A full steel sleeper track is too light for sustainable 19tal operations at 80kph and is not considered for mainline operations. Fully steel sleeper track may be utilised at low speed in sidings.

Some existing timber sleepers could be retained and plated as in Item 1 and 2 above, however, more than 75% are life expired. Any of those timber sleepers which could be retained will have to be cross bored for the new rail profile and will subsequently have a reduced life.

Replacement of the existing rail with 41kg/m effectively means that all timber sleepers must be replaced.

Enquiries with the timber industry has affirmed that sufficient treated timber sleepers (approx. 800,000 units) could be provided to meet the needs of this track upgrading,

Replacing all existing life expired sleepers with new timber sleepers plated as in item 1 above could be undertaken subject to the availability of sufficient numbers of plates and screw spikes (unit pricing is detailed in Section 8). However, over the 30-year life of the lines, all these new timber sleepers would have to be replaced again at least once, probably twice. With timber sleepered track, monitoring and maintenance are more intensive in an era where maintenance inputs are being minimised and suitably experienced resources are not so readily available. Constructing 760km of effectively new track in 1:2 steel/timber sleepers is not considered viable or sustainable.

Item 1 above is therefore not considered further.

Pricing per timber sleeper with resilient fastenings is significantly more expensive than providing low-profile concrete sleepers with resilient fastenings (refer Section 8). Additionally, all timber sleepers will require replacement at least once during the 30-year life of the project and are subject to a monitoring and maintenance regime similar to, but less than, for Item 1.

Item 2 above is therefore not considered further.

The most cost-effective track structure over the 30-year life is to use low-profile concrete sleepers to replace the existing timber sleepers. The existing steel sleepers are suitable for 41kg/m rail and could be retained.

The upgraded track structure, therefore, may be:

- 41kg CWR on 1:2 or 1:4 steel and low-profile concrete in metal ballast.

- 41kg CWR on low-profile concrete sleepers in metal ballast.

# Construction Methodology

7.1	Track Constructability Considerations

The issue is to determine the most efficient way to replace all rail (80lb or less) and the timber sleepers with low-profile concrete sleepers in gravel or metal ballast.

Gravel Ballast Sections.

The track is effectively being rebuilt. The gravel ballast must be graded out and the formation and shoulders compacted to retain the new metal ballast profile. The entire existing track structure must, therefore, be completely removed in advance. 

This then becomes completely new track construction, which is most effectively, efficiently and safely undertaken using a tracklaying machine. Recovering, handling and reloading steel sleepers into a tracklayer to achieve a 1:2 or 1:4 pattern steel and low-profile concrete sleeper track is not realistically achievable.

The strategy for estimating is, therefore, to reconstruct gravel ballast sections in metal ballast using 100% low-profile concrete sleepers with a fully mechanised tracklayer and to cascade the steel sleepers for reuse in retained CBH sidings. This will provide an appropriate track structure with minimum ongoing maintenance costs.

This strategy is also applied to Part 2 of the review for the Bruce Rock (part metal ballast), Kondinin (part metal ballast) and Trayning lines for conversion to SG.

Metal Ballast Sections

There are some sections of Tier 3 lines which are currently in metal ballast with 1:4 or 1:2 steel/timber sleepers and predominantly 60lb rail. These are Narrogin – Yilliminning; Bruce Rock – West Merredin; Narembeen – West Merredin; and Katanning - Badgebup. It is assumed that the existing minimum depth of metal ballast under the sleepers is 150mm, although, it is noted in many locations that the ballast has become fouled.

In these sections, a side insertion method for the low-profile concrete sleepers may be considered (Part A - Option B) to retain the existing steel sleepers in a 1:4 or 1:2 configuration. This method has been used in the past but only on sections with 41kg CWR rail and 1:2 steel/timber at regular spacing’s. With the retention of the steel sleepers, there is a saving on the number and hence cost of concrete sleepers.

However, the rail on the Tier 3 lines is primarily 60/63lb jointed in short or LWR lengths up to 110m. Joints are mostly staggered on adjacent rails and timber sleepers are used either side of each joint. Consequently, the distribution and spacing of the nominal 1:2 or1:4 steel is not consistent. To achieve an acceptable uniform track standard outcome, respacing of the steel sleepers will be necessary. The nature of steel sleepers is that they will require complete removal from the ballast and the ballast bed levelled before for replacing and respacing them.

This methodology (Option B) has been assessed as not viable for the metal ballast sections of the Tier 3 line upgrading. The pricing for Option B included in Appendix 8 does not include provision for the respacing of steel sleepers and is included for comparison purposes only.

The tracklayer methodology with 100% low profile concrete sleepers has again been adopted as the most efficient for upgrading these metal ballast sections. The downsides are the wastage of some of the existing metal ballast (partly fouled in any case), as it will have to be graded to a flat surface for placement of steel and concrete sleepers, and the removal of the fit for purpose steel sleepers. Again, they will be cascaded to other areas for reuse.

  - Methodology

Tracklaying

Rail siding depots would be established initially in Narrogin and subsequently West Merredin. These depot will include facilities for LWR and concrete sleeper stacking and handling to load the tracklaying train each day.

The Narrogin – Yilliminning – Corrigin; Yilliminning – Kulin; Tambellup – Gnowangerup; Katanning – Gnowangerup; and York – Quairading sections will be upgraded from Narrogin.

The West Merredin – Kondinin; West Merredin – Corrigin; and West Merredin – Trayning sections will upgraded from West Merredin.

The Perenjori – Maya section will be upgraded using a less mechanised method with LWR and sleepers coming direct to site from Perth.

Rail will come from the east on rail to the new FBW facility at Kenwick where it will be welded into LWR (110 – 175m) and transferred by rail to the rail depots at Narrogin or West Merredin for stacking, or direct to site on the Perenjori – Maya section.

Low-profile concrete sleepers will be manufactured in Perth and either road or rail hauled to the rail depots at Narrogin and West Merredin for stacking, or direct to site on the Perenjori – Maya section

Metal ballast will be road hauled from suitable quarries to stockpile at the nearest suitable rail loading siding immediately behind the rail head. From there it will be loaded into rail hoppers for daily distribution.

The tracklaying train will be loaded with rail and concrete sleepers each evening at the rail depot and proceed to site in the early morning to be available on site for commencement. A production rate of 1km per day is expected.

Rail will be site welded using a mobile FBW to provide full 41kg CWR.

Level Crossings

All public sealed level crossings will be upgraded to the new track standard ahead of tracklaying activities. Public unsealed and other crossings may be upgraded ahead of tracklaying if the road traffic usage requires, otherwise they will be treated as the tracklayer moves through. There is a 55mm increase in rail level due to the new track structure and the level crossings will be constructed high to allow for future tamping cycles to run into them, so, either the road or rail approaches will need to be regraded to allow for these factors.

Recommissioning of active protection will likely follow tracklaying. For construction trains, those crossings which currently have active protection will need protection using flagmen.

Bridges and Culverts

Replacement, strengthening or extending of bridges and culverts will be undertaken ahead of tracklaying activities. Local sections of track will be removed as necessary to allow this work to proceed efficiently.  It is essential that these are completed ahead to allow continuous progress of the tracklayer. 

Some ballast retention extensions to headwalls may follow tracklaying.

Formation Works

Embankments which require widening to retain the new upgraded track and any formation strengthening will be undertaken ahead of tracklaying activities. This will also establish construction access.

Compaction of gravel ballast on the formation shoulders will be undertaken ahead of tracklaying, and cleaning of cutting side widths following tracklaying.

Turnouts

Replacement of turnouts and the removal of redundant mainline turnouts will be undertaken ahead of tracklaying activities.

CBH Sidings

Upgrading of CBH sidings will be undertaken in conjunction with mainline tracklaying. This will allow the reuse of recovered steel sleepers and utilise ballasting and tamping resources associated with the tracklaying face.

# Basis of Estimates

Estimates have been prepared to a Class 4 level in accordance with the table below.

Estimates are based on the construction strategies outlined in Section 7.2.

Material Costs

| Item | Inclusions | Cost per unit |
| --- | --- | --- |
| Sleepers |  |  |
| NG low profile concrete | Sleepers & fastenings ex Welshpool | $103.00 |
| NG timber | Supply | $53.16 |
|  | Koppers treatment | $9.70 |
|  | Cast pandrol plates & all fastenings | $76.00 |
|  | Total | $138.86 |
| NG steel insulated | Including fastenings | $123.50 |
| NG steel uninsulated | Including fastenings | $101.90 |
| Rail |  |  |
| 41kg per metre | Per metre of rail | $71.81 |
| 50kg per metre | Per metre of rail | $79.58 |

Therefore, the most cost-efficient track structure to meet the proposed operating regime is 41kg rail on low profile concrete sleepers. This is used in the estimates.

Engineering Survey, Design and Documentation

Provision has been made in the estimates for full engineering survey and assessment of formation earthworks, level crossing drainage, bridges, culverts and CBH sidings.

Project Management and Superintendence

Provision has been made in the estimates for PTA Project Management and Superintendence costs.

Unplanned Risk and Contingency

As an engineering review, a 10% contingency has been allowed in the estimate.

The allowance provides for factors such as:

- Unidentified Regulatory and Utility Authority requirements.

- Formation and underlying ground conditions.

- Bridge foundation condition.

- Technical requirements.

Exclusions

Key exclusions from the cost estimate are:

- Any costs associated with negotiation, agreement or conditions imposed from CBH or Arc Infrastructure.

- Land Acquisition costs.

- Environmental approvals and regulations.

- Escalation (cost base is Q2 2020).

- Flora and fauna approvals.

- Goods and Services Tax.

- Heritage approvals and/or artefacts arising.

- Any works to existing services and utilities.

# Alternate Operational Strategies

There are other strategies which could be employed to resume train operations on the Tier 3 lines. These will require a reduction in the operating regime specified in the engineering review scope in Section 2. Evaluation of these alternate strategies are not part of this engineering review. They are identified for consideration only. Indicative costings have been provided in the estimates for Strategy 9.1 below.

  - Retain under the previous Operating Regime (existing track structure rehabilitated)

Under this strategy, the lines will be retained under the operating regime in place at the time train operations ceased and retains the existing track structure. This provides up to 0.75 MGTPA at 16tal at a maximum 30kph loaded with seasonal dry weather operation only on gravel ballast sections. The proposed train consist is retained as 1 CBH Class locomotive and 30 wagons.

Track will require upgrading in selected sections. 60lb rail will mostly be suitable for reuse, requiring only attention to joint condition (free frozen joints or upgrade to LWR or CWR) and isolated locations of corroded rail (assumed as 1km/100km) which has been buried.

75% - 100% of all timber sleepers will need to be replaced. They will be replaced like-for-like unplated or plated. Timber resleepering cycles will be necessary every 10-12 years thereafter. It has been confirmed with industry that sufficient timber sleepers can be supplied to meet this ongoing need.

Full ballast profiles will need to be reinstated and the entire section of track resurfaced.

All turnouts of 63lb or greater will be partially re-timbered and retained. Any 60lb turnouts on mainline will need to be replaced, although these are very few in number.

Existing steel and concrete bridge structures can be retained with minimal refurbishment. The bridges with timber superstructures will be replaced and those with timber substructures should be evaluated for replacement (50% replacement is allowed in cost estimates).

Many of the culverts can be retained without modification. Some will require headwall or pipe length extensions to retain a full ballast profile.

Level crossings will require resealing and opportunity should be taken to upgrade the track to 41kg/m on concrete sleepers. Active protection will be recommissioned.

Some 50% of formation embankments identified in Appendix 1 will still require widening to retain a full ballast profile. Washaway sections will be reconstructed and there will be minor drainage improvements.

The alterations proposed to primary and secondary CBH facilities and redundant sidings would be implemented as per Appendix 3 to suit the proposed train configuration and operation.

However, it must be recognised that this scenario comes with increased risk to train operations. Existing rail and rail joints are up to 100 years old, and although not necessarily life expired in terms of wear or fatigue, they will be more brittle and subject to breakages, particularly in gravel ballast sections. The track and structure assets will require a significantly higher degree of monitoring and maintenance input.

This strategy is low capital cost with high ongoing maintenance cost and does not provide an optimal train operating regime.

  - Upgrade to seasonal 19tal Operating Regime

If the minimum operating standard is 19tal at a maximum speed of 30kph loaded, for a seasonal dry weather line haul of 1MGTPA over a life of 30 years, then another lower cost option is possible.

This reduced speed and dry weather operation only, removes the need to replace the existing sections of gravel ballast with crushed metal ballast.

It still requires rerailing in 41kg/m CWR rail and resleepering to establish a 1:2 steel and timber sleeper track with resilient fastenings. It has been confirmed with industry that sufficient timber sleepers can be supplied to meet this ongoing need. All timber sleepers will be renewed under this scenario. Low-profile concrete sleepers are not recommended for use in gravel ballast.

Rehabilitation costs will be reduced. There will be a slight increase in monitoring and maintenance costs over the 30-year life as at least 1, and probably 2, timber resleepering cycles will be required.

Arc Infrastructure currently allow this operating regime on the Lake Grace to Newdegate section using recycled 80lb CWR rail on 1:2 steel and timber sleepers in gravel ballast.

Again, this is lower capital cost and higher ongoing monitoring and maintenance cost whilst providing some efficiency improvement in train operations through the 19tal.

# Appendix 1 – Formation Works

# Appendix 2 – Linear Asset Diagrams

# Appendix 3 – CBH Siding Configurations

# Appendix 4 – Bridge Works

# Appendix 5 – Level Crossings

# Appendix 6 – Culvert Works

# Appendix 7A – West Merredin Yard NG Option - Schematic

# Appendix 7B – West Merredin Yard SG Option – Schematic

# Appendix 8 –Estimate Breakdown

# Appendix 9 – GHD Bridge Report

# Appendix 10 – PTA Rail System Map